## Dashboard
GuardianIQ - 1 Week Implementation Plan
Scope | Concrete engineering deliverables required after Volume 1: PostgreSQL physical schema, API spec, mapping guide, React architecture, module build order, QA readiness
Plan Window | 08-Jul-2026 to 14-Jul-2026 | Team | Poorvith, Aayush, Pankaj, Project Manager | Reference | Phase 3 / Volume 1 relationship architecture | Target | End-to-end developer readiness
KPI | Formula / Value | Target | Owner | Status | Notes
Total Activities | 38 | 40+ | PM | Tracked | Includes DB, API, UI, mapping, QA and handover
Critical Path Items | 24 | All assigned | PM | Tracked | Critical deliverables must finish by Day 5/6
Completed Items | 0 | 100% | All | Open | Update daily
Blocked Items | 0 | 0 | PM | Open | Review every evening
Final Handover Pack | Volume 3 + Volume 4 + Volume 5 + Mapping + QA Pack | Ready by 14-Jul | PM | Planned | Formal handover to developers

## Detailed Plan
WBS | Workstream | Activity | Detailed Task Description | Deliverable | Owner | Support | Priority | Status | Start Date | End Date | Dependencies | Acceptance Criteria | Notes
1.1 | Project Management | Kickoff and scope lock | Align the team on what is required after Volume 1: DB schema, API spec, screen/API/DB mapping, React architecture, build order and QA pack. | Signed kickoff notes and sprint scope | Project Manager | All | Critical | Not Started | 08-Jul-2026 | 08-Jul-2026 | Volume 1 available | Scope confirmed; no ambiguity on sprint outcome | Start with 60-minute walkthrough
1.2 | Project Management | Create sprint control board | Create single tracker for task status, owner, blockers, dependency, daily progress and final sign-off. | Sprint control board | Project Manager | All | High | Not Started | 08-Jul-2026 | 08-Jul-2026 | Kickoff | Tracker shared with all owners | Use this workbook as base
1.3 | Database | Review current Phase 0-2 DB assets | Review existing core, registry, workflow, audit schemas to avoid duplicate entities and ensure Phase 3 relationship layer builds on top. | DB gap assessment | Aayush | Pankaj | Critical | Not Started | 08-Jul-2026 | 08-Jul-2026 | DB access | Current schema understood and gap list prepared
1.4 | Database | Define Phase 3 physical schema | Finalize physical tables required now: generic_relationships, object_responsibilities, relationship_validation_results, graph_snapshots, policy_bindings stub/bridge, evidence_links stub/bridge. | Schema design draft | Aayush | Pankaj | Critical | Not Started | 08-Jul-2026 | 09-Jul-2026 | DB gap assessment | Tables, columns, keys, statuses and ownership fields defined
1.5 | Backend | Define service modules | Confirm backend modules: relationship, responsibility, graph, validation, authorization bridge, audit integration, cache. | Backend module blueprint | Pankaj | Aayush | Critical | Not Started | 08-Jul-2026 | 09-Jul-2026 | Volume 1 | Module boundaries clear and implementation files listed
1.6 | Frontend | Define React route/module structure | Define frontend module structure for Relationship Explorer, object relationship panels, graph view, create relationship wizard, timeline and impact view. | React module structure | Poorvith | Aayush | High | Not Started | 08-Jul-2026 | 09-Jul-2026 | Volume 2A | Routes, components and layout approach approved
2.1 | Database | Write DDL migrations | Create database migration scripts for Phase 3 relationship tables with PKs, FKs where possible, tenant_id, status, effective dates, JSONB, indexes and audit-friendly columns. | DDL migration script | Aayush | Pankaj | Critical | Not Started | 09-Jul-2026 | 10-Jul-2026 | Schema design draft | Script runs successfully on dev DB
2.2 | Database | Create indexes and constraints | Add composite indexes for tenant/source/target/type/status, reverse lookup, lifecycle and time-aware relationship resolution. | Index and constraint script | Aayush | Pankaj | Critical | Not Started | 09-Jul-2026 | 10-Jul-2026 | DDL migrations | Relationship lookups and graph queries supported
2.3 | Database | Create seed/reference data | Seed relationship types, lifecycle states, responsibility types, validation rule categories and sample reference data. | Seed script | Aayush | Pankaj | High | Not Started | 09-Jul-2026 | 10-Jul-2026 | DDL migrations | Reference data visible and reusable by APIs/UI
2.4 | Backend | Implement ORM models | Create SQLAlchemy models/Pydantic schemas for relationship tables and reference data. | ORM and schema models | Pankaj | Aayush | Critical | Not Started | 09-Jul-2026 | 10-Jul-2026 | DDL migrations | Models compile and match DB columns
2.5 | Backend | Implement repositories | Create repository functions for create, update, find active, reverse lookup, scoped lookup, lifecycle lookup and audit timeline references. | Repository layer | Pankaj | Aayush | Critical | Not Started | 09-Jul-2026 | 10-Jul-2026 | ORM models | Repository unit tests pass
2.6 | Frontend | Prepare shell screens | Create shell pages for Relationship Explorer, Create Relationship Wizard, Object Relationship Panel and Graph View. | Frontend shell screens | Poorvith | Aayush | High | Not Started | 09-Jul-2026 | 10-Jul-2026 | React structure | Screens load with placeholder data and routing
3.1 | Backend | Relationship service CRUD | Implement create/update/list/detail/revoke/suspend/expire relationship service with transaction handling. | RelationshipService | Pankaj | Aayush | Critical | Not Started | 10-Jul-2026 | 11-Jul-2026 | Repository layer | CRUD APIs functional and audited
3.2 | Backend | Responsibility service | Implement owner/reviewer/approver/auditor assignment and active owner resolution. | ResponsibilityService | Pankaj | Aayush | Critical | Not Started | 10-Jul-2026 | 11-Jul-2026 | Relationship service | Owners and approvers can be resolved
3.3 | Backend | Validation engine MVP | Implement mandatory validation rules: source exists, target exists, tenant match, duplicate active relationship, effective dates, status transition, owner required. | ValidationEngine MVP | Pankaj | Aayush | Critical | Not Started | 10-Jul-2026 | 11-Jul-2026 | Repositories | Invalid relationships are blocked with clear messages
3.4 | Backend | Audit event integration | Every create/update/revoke/suspend/validation failure should publish audit events. | Audit integration | Pankaj | Aayush | Critical | Not Started | 10-Jul-2026 | 11-Jul-2026 | Relationship service | Audit events created for all state changes
3.5 | Frontend | Build Relationship Explorer list/table | Create searchable/filterable table of relationships with object type, source, target, lifecycle, scope, owner and actions. | Relationship Explorer UI | Poorvith | Aayush | High | Not Started | 10-Jul-2026 | 12-Jul-2026 | Shell screens | Table renders API data and supports filters
3.6 | Frontend | Build Create Relationship Wizard | Wizard to select source, relationship type, target, scope, responsibility, effective dates, metadata and review/submit. | Create Relationship Wizard | Poorvith | Aayush | High | Not Started | 10-Jul-2026 | 12-Jul-2026 | Shell screens | Wizard validates and submits to API
4.1 | Backend | Graph/resolver APIs | Implement governance context and graph APIs: direct relationships, reverse relationships, owners, policies, evidence, audit timeline, depth-limited graph. | Resolver and Graph APIs | Pankaj | Aayush | Critical | Not Started | 11-Jul-2026 | 12-Jul-2026 | Relationship CRUD | Graph APIs return nodes/edges and enforce depth limits
4.2 | Backend | Authorization bridge | Ensure write APIs call authorization checks and graph APIs hide unauthorized objects based on tenant, role, sensitivity and relationship scope. | Authorization checks | Pankaj | Aayush | Critical | Not Started | 11-Jul-2026 | 12-Jul-2026 | Core RBAC/ABAC foundation | Unauthorized operations are blocked
4.3 | Backend | OpenAPI contract draft | Document all relationship/responsibility/graph/validation APIs with request, response, errors, permissions and audit events. | Backend API specification | Aayush | Pankaj | Critical | Not Started | 11-Jul-2026 | 12-Jul-2026 | APIs implemented | API spec reviewed by frontend and QA
4.4 | Frontend | Object relationship panel | Create reusable panel to embed on AI Model, AI Agent, Workflow and Tool detail pages showing direct relationships and governance context. | Object Relationship Panel | Poorvith | Aayush | High | Not Started | 11-Jul-2026 | 12-Jul-2026 | Relationship APIs | Panel works with object_type/object_id props
4.5 | Frontend | Graph View MVP | Create simple node-edge graph/list hybrid view for selected object with relationship labels, status and risk indicator. | Graph View MVP | Poorvith | Pankaj | High | Not Started | 11-Jul-2026 | 13-Jul-2026 | Graph APIs | Graph view shows connected objects and depth control
5.1 | Mapping | Create screen/API/DB mapping matrix | Map each screen and component to API, service, repository, table, audit event and test scenario. | Mapping matrix | Aayush | Poorvith, Pankaj | Critical | Not Started | 12-Jul-2026 | 13-Jul-2026 | API spec and DB schema | Matrix covers all Phase 3 screens and APIs
5.2 | Frontend | Relationship timeline UI | Create timeline drawer/page to show lifecycle events, before/after change and actor/reason for relationship. | Timeline UI | Poorvith | Pankaj | Medium | Not Started | 12-Jul-2026 | 13-Jul-2026 | Audit API | Timeline renders audit events
5.3 | Backend | Performance and cache baseline | Add basic caching for stable ownership/policy/permission relationships and query limits for graph traversal. | Cache/performance baseline | Pankaj | Aayush | Medium | Not Started | 12-Jul-2026 | 13-Jul-2026 | Graph APIs | No uncontrolled graph query; cache invalidates on update
5.4 | QA | Prepare QA test cases | Convert Volume 1 validation and scenario playbook into executable API/UI/DB test cases. | QA test pack | Pankaj | Project Manager | Critical | Not Started | 12-Jul-2026 | 13-Jul-2026 | Mapping matrix | Test cases mapped to requirements
5.5 | Project Management | Mid-sprint review | Review completed DB/API/UI/mapping status; remove blockers and decide scope adjustments. | Mid-sprint decision log | Project Manager | All | High | Not Started | 12-Jul-2026 | 12-Jul-2026 | Tasks in progress | Critical path still achievable
6.1 | Integration | End-to-end relationship creation flow | Test complete flow: create relationship from UI → API → DB → validation → audit → explorer refresh. | Integrated E2E flow | Aayush | Poorvith, Pankaj | Critical | Not Started | 13-Jul-2026 | 13-Jul-2026 | UI + APIs ready | E2E create flow passes
6.2 | Integration | End-to-end graph/context flow | Test selected AI Agent/Workflow → relationship panel → governance context → graph view → audit timeline. | Integrated graph/context flow | Poorvith | Aayush, Pankaj | Critical | Not Started | 13-Jul-2026 | 13-Jul-2026 | Graph UI/API ready | Graph/context flow passes
6.3 | QA | Execute API and DB validation tests | Run API tests, DB checks, negative validation cases, duplicate/cross-tenant/expired relationship checks. | API/DB QA results | Pankaj | Aayush | Critical | Not Started | 13-Jul-2026 | 13-Jul-2026 | QA pack | Critical API and DB tests pass
6.4 | QA | Execute UI functional tests | Validate explorer, wizard, panels, graph view, timeline, error handling, empty/loading states. | UI QA results | Pankaj | Poorvith | High | Not Started | 13-Jul-2026 | 13-Jul-2026 | UI integrated | Critical UI tests pass
6.5 | Documentation | Prepare developer handover pack | Prepare compact handover: DB script location, API spec, UI routes, mapping matrix, test evidence and known limitations. | Developer handover pack | Project Manager | All | Critical | Not Started | 13-Jul-2026 | 14-Jul-2026 | Integration results | Handover pack ready for team
7.1 | QA | Regression and bug fixing | Close critical and high defects; retest failed scenarios. | Defect closure report | Pankaj | Aayush, Poorvith | Critical | Not Started | 14-Jul-2026 | 14-Jul-2026 | QA results | No open critical defects
7.2 | Project Management | Final UAT walkthrough | Walk through DB schema, APIs, UI flows, mapping matrix and QA evidence with PM and team. | UAT walkthrough notes | Project Manager | All | Critical | Not Started | 14-Jul-2026 | 14-Jul-2026 | Handover pack | Stakeholder sign-off captured
7.3 | Documentation | Finalize acceptance checklist | Confirm Definition of Done for DB, backend, frontend, integration, audit, security and QA. | Final acceptance checklist | Project Manager | Pankaj | High | Not Started | 14-Jul-2026 | 14-Jul-2026 | UAT walkthrough | Checklist completed and signed
7.4 | Delivery | Release candidate package | Package code branches, scripts, API docs, UI build, test evidence and open issue list. | Phase 3 release candidate | Aayush | Poorvith, Pankaj | Critical | Not Started | 14-Jul-2026 | 14-Jul-2026 | Defects closed | Release candidate ready
7.5 | Project Management | Next sprint backlog | Create backlog for next phase: advanced policy engine, evidence depth, graph analytics, full UI refinements and performance hardening. | Next sprint backlog | Project Manager | All | Medium | Not Started | 14-Jul-2026 | 14-Jul-2026 | Final sign-off | Backlog ready and prioritized

## Daily Sprint
Day | Date | Focus | Key Activities | Primary Owners | Expected End-of-Day Output | PM Checkpoint
Day 1 | 08-Jul-2026 | Alignment + Architecture Lock | Kickoff; schema gap review; backend module boundaries; React routes; sprint tracker | PM, Aayush, Pankaj, Poorvith | Scope locked, DB/API/UI approach agreed | Evening: confirm no open scope ambiguity
Day 2 | 09-Jul-2026 | DB + Backend Foundation | DDL migrations; indexes; seed data; ORM models; repositories; frontend shell | Aayush, Pankaj, Poorvith | DB and repository foundation ready | Review DB script execution
Day 3 | 10-Jul-2026 | Core Services + UI Start | Relationship CRUD; responsibility service; validation MVP; audit events; explorer and wizard UI | Pankaj, Poorvith | Core services and core screens in progress | Check API/UI integration blockers
Day 4 | 11-Jul-2026 | Graph + Authorization + API Contract | Graph/resolver APIs; authorization checks; OpenAPI draft; relationship panels; graph MVP | Pankaj, Aayush, Poorvith | Graph/context capabilities usable | Review API spec with frontend
Day 5 | 12-Jul-2026 | Mapping + QA Prep + Timeline | Screen/API/DB mapping; timeline UI; cache baseline; QA pack; mid-sprint review | Aayush, Pankaj, Poorvith, PM | Mapping matrix and QA test pack ready | Scope adjustment if required
Day 6 | 13-Jul-2026 | Integration + Testing | E2E create flow; graph/context flow; API/DB tests; UI tests; handover pack | All | Integrated working build | Confirm critical defects only
Day 7 | 14-Jul-2026 | Stabilization + Handover | Regression; UAT walkthrough; final acceptance; release candidate; next backlog | All | Phase 3 implementation package ready | Final sign-off

## RACI
Deliverable / Activity | Project Manager | Aayush | Pankaj | Poorvith | Notes
Sprint scope and control | A | C | C | C | PM owns delivery governance
Physical PostgreSQL schema | I | A/R | C | I | Aayush owns DB foundation
DDL migrations and seed data | I | A/R | C | I | Must run cleanly
Backend repositories and models | I | C | A/R | I | Pankaj owns backend engineering quality
Relationship service APIs | I | C | A/R | I | Audit and validation mandatory
OpenAPI/API spec | I | A/R | C | C | Aayush coordinates with frontend
React route/module structure | I | C | I | A/R | Poorvith owns frontend architecture
Relationship Explorer UI | I | C | C | A/R | Must bind to API
Create Relationship Wizard | I | C | C | A/R | Must include validation
Graph View MVP | I | C | C | A/R | Start simple
Screen/API/DB mapping matrix | A | R | C | C | Used by all developers
QA test pack | A | C | R | C | Pankaj owns testing evidence
UAT walkthrough and sign-off | A/R | C | C | C | Final delivery gate

## Deliverables
ID | Deliverable | Description | Owner | Due Date | Acceptance Criteria | Status
D1 | Sprint Scope & Control Board | Approved 1-week sprint plan with owners, statuses, dependencies and daily checkpoints. | Project Manager | 08-Jul-2026 | Scope agreed and tracker shared | Not Started
D2 | PostgreSQL Physical Schema | Tables, indexes, constraints, seed data and migration scripts for relationship layer. | Aayush | 10-Jul-2026 | Script runs cleanly; tables validated | Not Started
D3 | Backend API Specification | OpenAPI-style API contract for relationships, responsibilities, graph, validation and resolver APIs. | Aayush | 12-Jul-2026 | Frontend and QA can use without clarification | Not Started
D4 | Backend Services MVP | RelationshipService, ResponsibilityService, ValidationEngine, Graph/Resolver APIs and Audit integration. | Pankaj | 13-Jul-2026 | Core services pass API tests | Not Started
D5 | Frontend Core Screens MVP | Relationship Explorer, Create Relationship Wizard, Object Relationship Panel, Graph View and Timeline. | Poorvith | 13-Jul-2026 | Screens integrated with APIs | Not Started
D6 | Screen/API/DB Mapping Matrix | Requirement → screen → API → service → repository → table → audit event → test case mapping. | Aayush | 13-Jul-2026 | Mapping complete for all Phase 3 flows | Not Started
D7 | QA Test Pack & Results | API, DB, UI, security, graph and negative test cases with evidence placeholders/results. | Pankaj | 14-Jul-2026 | Critical tests pass; defects logged | Not Started
D8 | Developer Handover Pack | Final package with scripts, API docs, UI routes, test evidence and open issue list. | Project Manager | 14-Jul-2026 | Team can continue implementation without open dependency | Not Started

## Risks
Risk ID | Risk / Issue | Impact | Probability | Severity | Owner | Mitigation | Trigger / Early Warning | Status
R1 | DB schema mismatch with Phase 0-2 tables | Rework and API delays | Medium | High | Aayush | Review existing schemas before creating new tables | Duplicate entities or FK confusion | Open
R2 | Relationship service over-engineering | Missed 1-week timeline | Medium | High | Pankaj | Build MVP first: CRUD, validation, resolver, audit | Complex graph logic delays core APIs | Open
R3 | Frontend waiting for API completion | Poorvith blocked | High | Medium | Aayush | Provide mock API contract by Day 2/3 | UI screens have placeholders only | Open
R4 | Validation rules too broad for first sprint | Testing delays | Medium | Medium | Pankaj | Implement mandatory rules only in week 1 | Too many edge cases added mid-sprint | Open
R5 | Audit event integration missed | Governance traceability gap | Low | High | Pankaj | Audit event mandatory in Definition of Done | CRUD works but no audit events | Open
R6 | Graph view complexity | UI delays | Medium | Medium | Poorvith | Implement simple node-edge/list hybrid MVP | Canvas graph consumes time | Open
R7 | No single mapping source | Team confusion | Medium | High | Project Manager | Mapping matrix mandatory by Day 5 | Repeated clarification questions | Open
R8 | Scope creep into full policy engine | Timeline impact | Medium | High | Project Manager | Restrict policy to bindings/stubs; full policy engine later | New policy requirements appear | Open

## Acceptance Checklist
Area | Checklist Item | Owner | Required for Sign-off | Status | Evidence / Notes
Database | All Phase 3 tables created with tenant_id, status, effective dates and audit-friendly columns | Aayush | Yes | Not Started
Database | Composite indexes support source/target lookup and graph traversal | Aayush | Yes | Not Started
Database | Seed data for relationship types, lifecycle states and responsibility types available | Aayush | Yes | Not Started
Backend | Relationship CRUD APIs implemented and documented | Pankaj | Yes | Not Started
Backend | Validation engine blocks invalid/duplicate/cross-tenant/expired relationships | Pankaj | Yes | Not Started
Backend | Audit event generated for create/update/revoke/suspend/validation failure | Pankaj | Yes | Not Started
Backend | Graph and governance context APIs return scoped data with depth limits | Pankaj | Yes | Not Started
Frontend | Relationship Explorer supports search, filter, list and detail actions | Poorvith | Yes | Not Started
Frontend | Create Relationship Wizard validates and submits relationship payloads | Poorvith | Yes | Not Started
Frontend | Object Relationship Panel reusable for AI Model, Agent, Workflow and Tool pages | Poorvith | Yes | Not Started
Frontend | Graph View MVP displays nodes, edges, lifecycle and depth control | Poorvith | Yes | Not Started
Mapping | Screen/API/DB/Audit/Test mapping matrix complete | Aayush | Yes | Not Started
QA | Critical API, DB, UI and negative tests executed | Pankaj | Yes | Not Started
Project | Final UAT walkthrough completed and signed off | Project Manager | Yes | Not Started

## Mapping Guide
Requirement / Flow | Screen / Component | API | Backend Service | Repository / DB Object | Audit Event | Test Case Owner
Create relationship | Create Relationship Wizard | POST /api/v1/relationships | RelationshipService.create_relationship | generic_relationships | RELATIONSHIP_CREATED | Pankaj
List relationships | Relationship Explorer | GET /api/v1/relationships | RelationshipService.search_relationships | generic_relationships | GRAPH_TRAVERSAL_PERFORMED if graph | Pankaj
Revoke relationship | Relationship Detail Action | POST /api/v1/relationships/{id}/revoke | RelationshipService.revoke_relationship | generic_relationships | RELATIONSHIP_REVOKED | Pankaj
Assign owner | Responsibility Panel | POST /api/v1/responsibilities | ResponsibilityService.assign_owner | object_responsibilities | RESPONSIBILITY_ASSIGNED | Pankaj
Resolve governance context | Object Relationship Panel | GET /api/v1/objects/{type}/{id}/governance-context | RelationshipResolverService.resolve_governance_context | generic_relationships + audit_events | GOVERNANCE_CONTEXT_BUILT | Pankaj
Graph traversal | Graph View | GET /api/v1/graph/{type}/{id} | GraphService.build_graph | generic_relationships + graph_snapshots | GRAPH_TRAVERSAL_PERFORMED | Pankaj
Validate relationship | Wizard Review Step | POST /api/v1/relationships/validate | ValidationEngine.validate_payload | relationship_validation_results | RELATIONSHIP_VALIDATION_FAILED | Pankaj
View timeline | Relationship Timeline | GET /api/v1/objects/{type}/{id}/audit-trail | RelationshipAuditService.get_timeline | audit_events/entity_change_log | AUDIT_TIMELINE_VIEWED | Pankaj
Impact analysis | Impact View | POST /api/v1/graph/impact-analysis | GraphService.impact_analysis | relationship_graph_snapshots | IMPACT_ANALYSIS_PERFORMED | Pankaj

## Lists
Status | Priority | Owner | Workstream | RACI Role
Not Started | Critical | Project Manager | Database | R
In Progress | High | Aayush | Backend | A
Blocked | Medium | Pankaj | Frontend | C
At Risk | Low | Poorvith | Integration | I
Completed |  | All | QA
Deferred |  |  | Documentation
Project Management