## Dashboard
GuardianIQ — Policy + ENFORCE Layer ¦ 1-Week Implementation Plan
Window | 13-Aug-2026 to 19-Aug-2026 | Developers | Aayush + Pankaj | Managed by | Jitendra | Objective | Working MVP + QA evidence + handover
KPI | Value | Target | Owner | Gate | Formula/Definition | Status | Notes
Total Detailed Activities | 31 | >= 30 | Jitendra | Tracked | All implementation + QA + handover tasks | Open
Critical Activities | 23 | 100% complete | Jitendra | Go/No-Go | No Critical item deferred without approval | Open
Completed Activities | 0 | 100% | Aayush + Pankaj | Daily | Updated by owners | Open
Blocked Activities | 0 | 0 | Jitendra | Daily | Escalate same day | Open
QA Tests | 22 | >= 20 | Pankaj | Day 7 | Critical/negative/security coverage | Open
QA Passed | 0 | All Critical | Pankaj | Go/No-Go | No failed Critical test | Open
Key Deliverables | 10 | 10 | Jitendra | Day 7 | D1-D10 | Open
Release Candidate | Policy + Enforcement MVP | Day 7 | Jitendra | Final | UAT + handover complete | Planned
Resource | Primary Accountability | Planned Sprint Load | Daily PM Expectation
Aayush | DB + hard enforcement + integration + frontend MVP + handover | ~52.5 hrs | Daily EOD demo / committed artifacts
Pankaj | Policy engine + gateway + authorization + QA/security | ~52.5 hrs | Daily code/test evidence
Jitendra | Scope/dependencies/defects/UAT/sign-off | ~14 hrs management | 2 checkpoints/day + blocker removal

## Detailed Plan
WBS | Day | Workstream | Activity | Detailed Implementation Steps | Primary Owner | Support | Est. Hrs | Start Date | End Date | Dependency | Deliverable / Output | Acceptance Criteria | Priority | Status | Jitendra Checkpoint
1.1 | Day 1 | Project Management | Kickoff and implementation scope freeze | Walk through both developer specs; freeze one-week MVP scope; confirm no feature expansion; confirm branches, DB environment, API naming, event catalogue, approval dependency, Definition of Done. | Jitendra | Aayush + Pankaj | 1 | 13-Aug-2026 | 13-Aug-2026 | Developer specs handed over | Signed sprint scope + decision log | All in-scope modules, dependencies and acceptance gates explicitly confirmed. | Critical | Not Started | 13:00 scope lock; 18:00 blocker review
1.2 | Day 1 | Architecture | Freeze v1 domain enums and runtime contract | Freeze PolicyStatus, VersionStatus, BindingStatus, Decision, TargetType, VersionStrategy, AutonomyLevel, AccessMode, DataOperation, Classification, EnforcementMode; freeze GovernedRuntimeRequest and enforcement response contract. | Pankaj | Aayush | 2 | 13-Aug-2026 | 13-Aug-2026 | 1.1 | v1 enums + request/response contract | Same enums/contracts used by DB, backend and frontend; no duplicate naming. | Critical | Not Started | Review enum/contract sheet before coding
1.3 | Day 1 | Database | Gap review against existing Phase 0-4 schema | Inspect existing policy/relationship/workflow/registry/audit tables; identify reusable entities vs new tables; map existing GOVERNED_BY, USES_TOOL, USES_DATA_SOURCE relationships; avoid duplicate sources of truth. | Aayush | Pankaj | 2.5 | 13-Aug-2026 | 13-Aug-2026 | 1.1 | DB gap assessment | Existing objects reused where appropriate; migration list approved. | Critical | Not Started | DB review outcome recorded
1.4 | Day 1 | Database | Finalize physical schema and migration order | Finalize governance_policies, policy_versions, policy_rules, policy_bindings, policy_evaluations, policy_rule_evaluations, policy_exceptions, enforcement_decisions, agent_runtime_boundaries, tool_capabilities, agent_tool_permissions, data_source_fields, agent_data_permissions, runtime_authorizations, runtime_enforcement_log. | Aayush | Pankaj | 3 | 13-Aug-2026 | 14-Aug-2026 | 1.3 | Physical model + migration order | PK/FK/tenant/status/effective-date rules agreed; migration is additive and reversible. | Critical | Not Started | Approve table list and ownership
2.1 | Day 2 | Database | Create and run PostgreSQL migrations | Create tables, enums/check constraints, FKs where stable, tenant_id, timestamps, lifecycle fields; add required indexes for binding resolution, policy evaluation history, agent/tool/data permission lookup and runtime correlation. | Aayush | Pankaj | 5 | 14-Aug-2026 | 14-Aug-2026 | 1.4 | Migration scripts executed in dev | Clean migration on dev DB; rollback/re-run tested; no existing data broken. | Critical | Not Started | 11:30 migration validation
2.2 | Day 2 | Database | Seed reference data | Seed policy types, decisions, binding target types, autonomy levels, access modes, classifications, transformations, enforcement modes and sample pilot policy/tool/data capability records. | Aayush | Pankaj | 1.5 | 14-Aug-2026 | 14-Aug-2026 | 2.1 | Seed script + pilot seed data | Backend can load reference data; pilot scenario has required master data. | High | Not Started | Verify seeds after migration
2.3 | Day 2 | Backend Core | Create backend module skeletons | Create policy_engine, enforcement, agent_boundary, tool_governance, data_governance modules with models/schemas/repository/service/router; wire dependency injection and route registration. | Pankaj | Aayush | 3 | 14-Aug-2026 | 14-Aug-2026 | 1.2,2.1 | Backend module shells | Application starts; routes compile; module boundaries match specification. | Critical | Not Started | 16:00 code structure review
2.4 | Day 2 | Backend Core | Implement repositories and tenant-safe query patterns | Implement policy/version/rule/binding repositories; boundary/tool/data permission repositories; common same-tenant filters, effective-date helpers, status filters and pagination. | Pankaj | Aayush | 3.5 | 14-Aug-2026 | 15-Aug-2026 | 2.1,2.3 | Repository layer | Repository tests prove tenant isolation and lifecycle filtering. | Critical | Not Started | Repository review before services
3.1 | Day 3 | Policy Engine | Implement Policy and Version lifecycle service | Create policy, create draft version, validate rules, activate immutable version, supersede previous version, suspend/retire policy; prevent mutation of ACTIVE version; publish lifecycle events through existing event publisher. | Pankaj | Aayush | 4 | 15-Aug-2026 | 15-Aug-2026 | 2.4 | Policy/Version Service | Lifecycle transitions and immutability tests pass; audit events emitted. | Critical | Not Started | Review lifecycle tests
3.2 | Day 3 | Policy Engine | Implement Policy Binding Service | Create/activate/suspend/revoke binding; validate target exists, same tenant, effective dates, duplicate overlap, priority, mandatory flag, CURRENT_ACTIVE vs PINNED_VERSION; invalidate binding cache. | Pankaj | Aayush | 3.5 | 15-Aug-2026 | 15-Aug-2026 | 2.4 | Policy Binding Service | Direct binding works for agent/model/workflow/tool/data; invalid/cross-tenant bindings blocked. | Critical | Not Started | Demo one direct binding
3.3 | Day 3 | Policy Engine | Implement Binding Resolver | Resolve direct + workflow + BU/department + tenant mandatory bindings; filter ACTIVE/effective/scope/conditions; select policy versions; apply precedence; return resolution_hash and trace. | Pankaj | Aayush | 3.5 | 15-Aug-2026 | 16-Aug-2026 | 3.2 | Policy Resolver | Resolved set is deterministic and explainable; expired/inactive bindings excluded. | Critical | Not Started | Review precedence output
3.4 | Day 3 | Policy Engine | Implement safe rule evaluator + decision combiner | Implement allow-listed AST/operators (EQ/NE/GT/GTE/LT/LTE/IN/EXISTS/CONTAINS/ALL/ANY/NOT); record per-rule results; combine DENY > REQUIRE_APPROVAL > ESCALATE > ALLOW_WITH_OBLIGATIONS > ALLOW. | Pankaj | Aayush | 4 | 15-Aug-2026 | 16-Aug-2026 | 3.1,3.3 | Rule evaluator + combiner | No arbitrary code execution; deterministic result; rule-level explanation persisted. | Critical | Not Started | Decision precedence reviewed
4.1 | Day 4 | Enforcement | Implement Agent Boundary Resolver | Resolve active agent runtime boundary; enforce status, autonomy level, kill switch, allowed/blocked operations, environments, model list, data classes, transaction/record/rate limits. | Aayush | Pankaj | 3 | 16-Aug-2026 | 16-Aug-2026 | 2.4 | Agent Boundary Service | RECOMMEND_ONLY and kill-switch blocks validated; effective-date behavior works. | Critical | Not Started | Demo boundary block
4.2 | Day 4 | Enforcement | Implement Tool Capability & Permission Guard | Register capabilities; match agent+tool+capability+access_mode+environment; validate parameter constraints, max value/records, approval flag; use active USES_TOOL relationship as prerequisite. | Aayush | Pankaj | 3.5 | 16-Aug-2026 | 16-Aug-2026 | 2.4,4.1 | Tool Guard | READ cannot execute WRITE; missing capability denied; parameter constraints enforced. | Critical | Not Started | Demo READ vs WRITE
4.3 | Day 4 | Enforcement | Implement Data Permission Guard and transformations | Resolve USES_DATA_SOURCE; validate purpose, operation, classification ceiling, allowed/denied fields, row scope, max records/export; implement MASK/REDACT/TOKENIZE/HASH hooks using test data. | Aayush | Pankaj | 4 | 16-Aug-2026 | 17-Aug-2026 | 2.4,4.1 | Data Guard + transformation hooks | Denied fields never exposed; masking occurs before model/tool exposure; record limits enforced. | Critical | Not Started | Data masking demo
4.4 | Day 4 | Enforcement | Implement Model/Provider Guard | Validate USES_MODEL, active approved model/version, provider restrictions, environment/region and data-classification compatibility; block unauthorized fallback model. | Aayush | Pankaj | 2 | 16-Aug-2026 | 17-Aug-2026 | 4.1,4.3 | Model Guard | Restricted-data/provider incompatibility blocked before invocation. | High | Not Started | Provider restriction test
5.1 | Day 5 | Enforcement | Build Governance Context Builder and Decision Combiner integration | Normalize runtime request; gather actor/agent/workflow/model/tool/data/risk/environment context; call relationship guard, hard boundaries and policy engine; combine into one authoritative result with reason codes and obligations. | Pankaj | Aayush | 3.5 | 17-Aug-2026 | 17-Aug-2026 | 3.4,4.1-4.4 | Governance Context + combined decision | One request produces layer-by-layer trace and one final decision. | Critical | Not Started | Review final decision trace
5.2 | Day 5 | Enforcement | Implement Runtime Enforcement Gateway | Server-side mandatory gateway for governed WRITE/EXECUTE; route DENY to block, REQUIRE_APPROVAL to approval adapter, ESCALATE to escalation adapter, ALLOW to controlled adapter; never let client call target directly. | Pankaj | Aayush | 4 | 17-Aug-2026 | 17-Aug-2026 | 5.1 | Runtime Enforcement Gateway | Target adapter is invoked only after successful enforcement decision. | Critical | Not Started | Live controlled action demo
5.3 | Day 5 | Security | Implement exact-request authorization / TOCTOU protection | Create context_hash, relationship_hash, policy_hash; issue short-lived runtime authorization linked to request/approval; verify immediately before target execution; reject changed/replayed/expired authorization. | Pankaj | Aayush | 3 | 17-Aug-2026 | 18-Aug-2026 | 5.2 | Runtime Authorization Service | Changed request after approval is rejected; replay blocked for single-use authorization. | Critical | Not Started | Security test review
5.4 | Day 5 | Integration | Integrate approval/exception hooks | Integrate REQUIRE_APPROVAL with existing approval service; pass policy/version/rule/context hash; validate approval at execution time; support exception lookup. If full 2-layer approval work is separate, use stable adapter contract and test stub until merged. | Aayush | Pankaj | 2.5 | 17-Aug-2026 | 18-Aug-2026 | 5.1, approval service | Approval/Exception Adapter | Pending approval prevents execution; approved unchanged context can proceed. | High | Not Started | Dependency status checkpoint
5.5 | Day 5 | Integration | Extend governance event integration | Publish POLICY_EVALUATED/TRIGGERED, AGENT_ACTION_REQUESTED/VALIDATED/BLOCKED, TOOL_ACCESS_ATTEMPTED/DENIED, DATA_ACCESS_REQUESTED/DENIED, DATA_TRANSFORMATION_APPLIED, MODEL_INVOCATION_BLOCKED, ACTION_EXECUTED/FAILED with correlation_id. | Aayush | Pankaj | 2.5 | 17-Aug-2026 | 18-Aug-2026 | 5.1, Step 4 event publisher | Event integration | Complete event chain visible for pilot request; no sensitive raw payload in event. | Critical | Not Started | Audit timeline check
5.6 | Day 5 | Frontend | Build minimal Policy & Binding administration UI | Implement policy list/detail, active version summary, binding manager/attach policy drawer, applicable policies panel; use existing design system; backend remains authoritative. | Aayush | Pankaj | 4 | 17-Aug-2026 | 18-Aug-2026 | 3.1-3.3 APIs | Policy/Binding UI MVP | User can attach policy to agent/workflow/tool/data and see direct/inherited source. | High | Not Started | UI/API review
6.1 | Day 6 | Frontend | Build Agent Boundary / Tool / Data access tabs | On Agent Detail add Autonomy & Limits, Tool Access, Data Access, Policies, Enforcement History; implement grant/revoke forms and kill-switch control with permission checks. | Aayush | Pankaj | 4.5 | 18-Aug-2026 | 18-Aug-2026 | 4.1-4.3 APIs | Agent enforcement UI MVP | Configured boundary and entitlements visible/editable by authorized admin. | High | Not Started | Functional UI demo
6.2 | Day 6 | Frontend | Build Enforcement Simulation and Decision Detail | Create NON-AUTHORITATIVE simulation screen; display relationship/boundary/policy checks, matched rules, final decision, obligations and remediation hint; no target side effect. | Aayush | Pankaj | 3 | 18-Aug-2026 | 18-Aug-2026 | 5.1 API | Simulation + decision trace UI | Simulation never executes target; trace is understandable to developer/support user. | Medium | Not Started | Simulation demo
6.3 | Day 6 | QA | Backend/API automated test suite | Create/execute unit and API tests for policy lifecycle, binding resolution, decision precedence, boundary rules, tool permissions, data classification/transforms, model restrictions, authorization replay/context mismatch and tenant isolation. | Pankaj | Aayush | 5 | 18-Aug-2026 | 18-Aug-2026 | 3.x,4.x,5.x | Automated API test results | All Critical test cases pass or defects logged with owner/ETA. | Critical | Not Started | 15:00 test triage
6.4 | Day 6 | QA | End-to-end integration scenarios | Execute pilot flows: permitted action; missing WRITE permission; high-value approval; restricted data to prohibited model; masking obligation; permission revoked after approval; kill switch; policy engine timeout fail-closed. | Pankaj | Aayush | 3.5 | 18-Aug-2026 | 18-Aug-2026 | 5.2-5.5 | E2E test evidence | No unauthorized target call occurs in negative scenarios; event trail complete. | Critical | Not Started | 18:00 critical defect review
7.1 | Day 7 | Security | Security and negative-path validation | Verify cross-tenant isolation, agent spoof prevention, inactive/expired permission behavior, unauthorized admin changes, no secret leakage, raw sensitive payload excluded from logs/events, service-only authoritative evaluation. | Pankaj | Aayush | 3 | 19-Aug-2026 | 19-Aug-2026 | 6.3,6.4 | Security validation pack | No Critical security gap open. | Critical | Not Started | Security sign-off
7.2 | Day 7 | Integration | Performance/cache/resilience hardening | Add targeted caches for active versions/bindings/boundaries/permissions; invalidate on changes; DB fallback on cache failure; enforce timeouts; capture evaluation latency; validate fail-closed rules. | Aayush | Pankaj | 3 | 19-Aug-2026 | 19-Aug-2026 | 5.x,6.x | Performance/resilience baseline | Common path acceptable; cache failure does not bypass controls. | High | Not Started | Performance review
7.3 | Day 7 | QA | Regression and defect closure | Retest all Critical/High defects; run smoke suite for prior registry/workflow/relationship/event capabilities affected by new integrations; document deferred non-critical items. | Pankaj | Aayush | 3.5 | 19-Aug-2026 | 19-Aug-2026 | 6.3,6.4,7.1 | Regression report | Zero open Critical defects; High defects either closed or explicitly accepted by Jitendra. | Critical | Not Started | 16:00 go/no-go
7.4 | Day 7 | Documentation | Finalize developer handover pack | Package DB migrations, seed scripts, OpenAPI, event extensions, config/env notes, sample policies/permissions, curl/Postman examples, test evidence, known issues, rollback and runbook. | Aayush | Pankaj | 2.5 | 19-Aug-2026 | 19-Aug-2026 | All implementation | Handover pack | A new developer can run migrations, start services and execute pilot scenario without clarification. | High | Not Started | Handover completeness check
7.5 | Day 7 | Project Management | Final UAT / Green flag review | Jitendra walks the pilot scenario end to end: attach policy -> configure agent/tool/data -> simulate -> approval/block/allow -> target adapter -> events/audit; review checklist and sign off remaining backlog. | Jitendra | Aayush + Pankaj | 1.5 | 19-Aug-2026 | 19-Aug-2026 | 7.1-7.4 | Signed sprint acceptance + next backlog | All mandatory acceptance criteria met; release candidate tagged. | Critical | Not Started | Final sign-off

## Daily Sprint
Day | Date | Primary Theme | Aayush Focus | Pankaj Focus | Jitendra Management Gate | Expected EOD Output | Exit Gate
Day 1 | 13-Aug-2026 | Architecture + DB freeze | DB gap review, physical model, migration order | Enums/contracts, service architecture, implementation rule freeze | Kickoff; freeze scope; remove ambiguities; approve schema list | Frozen v1 contract + physical DB design | No schema/API ambiguity
Day 2 | 14-Aug-2026 | Database + backend foundation | Migrations, indexes, seeds; support repository model mapping | Module shells, repositories, tenant/effective-date query helpers | Validate migrations and repository plan | DB ready + backend foundation compiling | Clean migration and app startup
Day 3 | 15-Aug-2026 | Policy core | Support DB/API integration and test data | Policy/version lifecycle, binding, resolver, safe rule evaluator/combiner | Review precedence and lifecycle demo | Policies can be bound, resolved and evaluated | Deterministic policy decision
Day 4 | 16-Aug-2026 | Agent/Tool/Data boundaries | Agent boundary, tool permissions, data permission/transforms, model guard | Review hard-boundary integration; add tests and edge cases | Validate three boundary demos | Hard entitlements enforce before policy | Unauthorized request blocked
Day 5 | 17-Aug-2026 | Runtime gateway + integration | Approval adapter, events, minimal policy/binding UI | Context builder, enforcement gateway, exact-request authorization | Midpoint architecture review; dependency escalation | One end-to-end governed runtime flow | Target called only after authorization
Day 6 | 18-Aug-2026 | Frontend MVP + QA | Agent tabs, permission UI, simulation/decision trace | Automated tests + E2E negative/positive scenarios | Defect triage; protect critical path | Feature-complete MVP with test evidence | Critical test set mostly green
Day 7 | 19-Aug-2026 | Hardening + handover | Performance/cache/resilience, docs/handover | Security, regression, defect closure | Go/no-go, UAT, sign-off, next backlog | Release candidate + handover pack | Zero Critical defects

## Resource Load
Resource | Role in Sprint | Primary Areas | Planned Hours | Critical Deliverables | Day 1-3 | Day 4-5 | Day 6-7
Aayush | Backend/DB + partial frontend | Physical DB, migrations, agent/tool/data enforcement, integration, frontend MVP, performance/handover | 52.5 | DB migration; Boundary/Tool/Data services; Approval/Event integration; Frontend MVP; Handover | DB + integration support | Enforcement + integration | Frontend + performance/docs
Pankaj | Backend + QA | Policy engine, resolver/evaluator, enforcement gateway, authorization, automated QA/security/regression | 52.5 | Policy Engine; Runtime Gateway; Authorization; Automated/E2E QA; Security sign-off | Backend core + policy | Gateway + authorization | QA + security/regression
Jitendra | Project Manager | Scope, dependencies, daily gates, blocker removal, UAT, sign-off | 14 | Scope freeze; daily checkpoint; go/no-go; acceptance and backlog | Scope and architecture gates | Dependency/defect gates | UAT + sign-off

## Deliverables
ID | Deliverable | Owner | Due | Depends On | Acceptance Gate | Status | Jitendra Sign-off
D1 | Frozen v1 enums + runtime request/response contract | Pankaj | 13-Aug-2026 | Kickoff | Used consistently in schema/API/tests | Not Started | Pending
D2 | Physical PostgreSQL schema + migration/rollback + seeds | Aayush | 14-Aug-2026 | D1 | Clean migration/rollback; existing data safe | Not Started | Pending
D3 | Policy/Version/Binding/Resolver/Evaluator services | Pankaj | 16-Aug-2026 | D1,D2 | Policy can attach -> resolve -> evaluate deterministically | Not Started | Pending
D4 | Agent Boundary + Tool + Data + Model guards | Aayush | 17-Aug-2026 | D2 | Hard boundaries block unauthorized calls | Not Started | Pending
D5 | Runtime Enforcement Gateway + exact-request authorization | Pankaj | 18-Aug-2026 | D3,D4 | Target adapter cannot execute without valid authorization | Not Started | Pending
D6 | Approval/Exception + Governance Event integration | Aayush | 18-Aug-2026 | D3,D5 | Approval and audit chain work with correlation_id | Not Started | Pending
D7 | Policy/Enforcement frontend MVP | Aayush | 18-Aug-2026 | D3-D6 APIs | Admin can configure/view; simulation has no side effect | Not Started | Pending
D8 | Automated + E2E + security test evidence | Pankaj | 19-Aug-2026 | D3-D7 | All Critical tests pass; zero Critical defects | Not Started | Pending
D9 | Performance/resilience baseline + handover pack | Aayush | 19-Aug-2026 | D3-D8 | Cache fallback/fail-closed documented; handover runnable | Not Started | Pending
D10 | Final UAT and sprint acceptance | Jitendra | 19-Aug-2026 | D1-D9 | Green flag + next backlog | Not Started | Pending

## RACI
Work Package | Jitendra | Aayush | Pankaj | Final Accountable | Notes
Scope / architecture decisions | A/R | C | C | Jitendra | No implementation ambiguity remains
Physical DB & migrations | I | A/R | C | Aayush | Pankaj reviews model compatibility
Policy lifecycle / binding / resolution / evaluation | I | C | A/R | Pankaj | Aayush supports DB/integration
Agent Boundary / Tool / Data / Model guards | I | A/R | C | Aayush | Pankaj provides QA/security review
Runtime Enforcement Gateway | I | C | A/R | Pankaj | Server-side authoritative control
Approval / exception integration | A | R | C | Jitendra | Adapter contract if dependency not merged
Governance event integration | I | A/R | C | Aayush | Must follow Step 4 event/outbox pattern
Frontend MVP | I | A/R | C | Aayush | Only developer/admin UI required this sprint
Automated / E2E / security QA | A | C | R | Jitendra | Pankaj owns evidence and regression
Performance / resilience | I | R | C | Aayush | No bypass on cache/dependency failure
Handover / release candidate | A | R | R | Jitendra | Both developers provide artifacts

## QA & Acceptance
Test ID | Area | Scenario | Expected Result | Owner | Run Day | Status | Evidence / Defect
Q-001 | Policy | Bind policy to active AI Agent | Binding active and visible; audit event created | Pankaj | Day 3 | Not Run
Q-002 | Policy | Expired binding resolution | Expired binding excluded | Pankaj | Day 3 | Not Run
Q-003 | Policy | DENY vs ALLOW conflict | DENY wins | Pankaj | Day 3 | Not Run
Q-004 | Policy | REQUIRE_APPROVAL vs ALLOW | Approval required | Pankaj | Day 3 | Not Run
Q-005 | Agent | RECOMMEND_ONLY attempts WRITE | Denied before target call | Pankaj | Day 4 | Not Run
Q-006 | Agent | Kill switch active | All governed actions blocked | Pankaj | Day 4 | Not Run
Q-007 | Tool | READ permission attempts WRITE | Denied | Pankaj | Day 4 | Not Run
Q-008 | Tool | Parameter above permission max | Denied/approval as configured | Pankaj | Day 4 | Not Run
Q-009 | Data | Wrong purpose requested | Denied | Pankaj | Day 4 | Not Run
Q-010 | Data | Denied field requested | Filtered/denied; never exposed | Pankaj | Day 4 | Not Run
Q-011 | Data | Masking obligation | Masked before model/tool exposure | Pankaj | Day 5 | Not Run
Q-012 | Model | Restricted data + prohibited provider | Blocked before provider call | Pankaj | Day 5 | Not Run
Q-013 | Approval | High-value request requires approval | No execution before approval | Pankaj | Day 6 | Not Run
Q-014 | Authorization | Request changed after approval | Context hash mismatch; re-evaluate | Pankaj | Day 6 | Not Run
Q-015 | Authorization | Replay single-use authorization | Rejected | Pankaj | Day 6 | Not Run
Q-016 | Security | Cross-tenant binding/permission query | Blocked/no data | Pankaj | Day 6 | Not Run
Q-017 | Security | Spoofed agent ID/runtime principal | Rejected | Pankaj | Day 7 | Not Run
Q-018 | Resilience | Cache unavailable | Authoritative DB fallback; no bypass | Pankaj | Day 7 | Not Run
Q-019 | Resilience | Policy engine timeout critical WRITE | Fail closed | Pankaj | Day 7 | Not Run
Q-020 | Audit | Complete runtime correlation | Request-policy-approval-action events share correlation_id | Pankaj | Day 7 | Not Run
Q-021 | Frontend | Simulation run | No target side effect | Pankaj | Day 6 | Not Run
Q-022 | Regression | Existing registry/workflow/relationship flow | No critical regression | Pankaj | Day 7 | Not Run

## Risks & Dependencies
ID | Type | Risk / Dependency | Impact | Owner | Required By | Mitigation / Decision | Status | Jitendra Action
R-01 | Dependency | Existing approval service / 2-layer approval may be under separate development | Runtime REQUIRE_APPROVAL integration may block E2E flow | Jitendra | 17-Aug-2026 | Freeze adapter contract Day 1; use stub/mock if merge not ready; integration after stable API. | Open | Confirm owner/API today
R-02 | Dependency | Step 4 event publisher/outbox availability | Audit event integration delayed | Aayush | 17-Aug-2026 | Use existing event publisher; if incomplete, wrap through interface and persist integration TODO without changing event contract. | Open | Confirm event service branch
R-03 | Risk | Trying to build full enterprise policy authoring UX in one week | Critical backend scope delayed | Jitendra | 13-Aug-2026 | Limit frontend to developer/admin MVP: policy list/detail, binding, agent tabs, simulation/history. | Open | Protect scope
R-04 | Risk | Duplicate data model vs existing relationship/policy tables | Future inconsistency | Aayush | 13-Aug-2026 | Complete DB gap assessment before migrations; reuse canonical objects where stable. | Open | Approve migration list
R-05 | Risk | Arbitrary policy expression execution | Security vulnerability | Pankaj | 15-Aug-2026 | Only allow-listed condition AST/operators; never eval Python/JS. | Open | Security checkpoint
R-06 | Risk | Frontend or caller bypasses enforcement gateway | Governance failure | Pankaj | 17-Aug-2026 | Target adapters callable only through server-side enforcement service for governed operations. | Open | Architecture review
R-07 | Risk | Sensitive fields copied into events/logs | Privacy exposure | Pankaj | 18-Aug-2026 | Store references/normalized facts only; masking rules; explicit negative test. | Open | Review event payload
R-08 | Risk | Cache returns stale permission after revoke/kill switch | Unauthorized execution | Aayush | 19-Aug-2026 | Invalidate on critical changes; immediate DB/recheck for high-risk execute path. | Open | Resilience check
R-09 | Risk | One-week schedule leaves limited UI polish | User experience not production-ready | Jitendra | 19-Aug-2026 | Accept developer/admin MVP; capture UI polish in next sprint. | Open | Set expectation

## Handover Checklist
# | Handover Artifact | Owner | Required | Status | Location / Notes
1 | DB migrations + rollback scripts | Aayush | Yes | Not Started
2 | Reference seed data / pilot sample data | Aayush | Yes | Not Started
3 | OpenAPI contracts + example payloads | Pankaj | Yes | Not Started
4 | Policy rule/operator schema | Pankaj | Yes | Not Started
5 | Binding resolution precedence documented | Pankaj | Yes | Not Started
6 | Agent boundary/tool/data permission API examples | Aayush | Yes | Not Started
7 | Runtime Enforcement Gateway sequence/runbook | Pankaj | Yes | Not Started
8 | Approval/exception adapter contract | Aayush | Yes | Not Started
9 | Event catalogue extensions / schema registry updates | Aayush | Yes | Not Started
10 | Frontend route/component list | Aayush | Yes | Not Started
11 | QA evidence / automated test report | Pankaj | Yes | Not Started
12 | Security and fail-closed test evidence | Pankaj | Yes | Not Started
13 | Known issues / deferred backlog | Jitendra | Yes | Not Started
14 | Deployment / rollback / configuration notes | Aayush | Yes | Not Started
15 | Final UAT sign-off | Jitendra | Yes | Not Started

## Lists
Status | Priority | Owner | Workstream | RACI | Test Status
Not Started | Critical | Jitendra | Project Management | R | Not Run
In Progress | High | Aayush | Architecture | A | Pass
Blocked | Medium | Pankaj | Database | C | Fail
At Risk | Low | Aayush + Pankaj | Backend Core | I | Blocked
Completed |  |  | Policy Engine |  | Retest
Deferred |  |  | Enforcement
On Hold |  |  | Frontend
Integration
QA
Security
Documentation