## Executive Summary
GuardianIQ Phase 0 & Phase 1 – 12 Day Implementation Plan
Project | GuardianIQ |  |  |  | Plan Metrics | Value | Notes
Scope | Phase 0 Foundation Setup + Phase 1 Governance Registry |  |  |  | Total Activities | 48 | Detailed executable tasks
Timeline | 19-May-2026 to 30-May-2026 |  |  |  | Phase 0 Activities | 16 | Foundation tasks
Duration | 12 calendar days |  |  |  | Phase 1 Activities | 24 | Registry build tasks
Team Model | 4 implementation resources + 1 Project Manager |  |  |  | Stabilization/Closure Activities | 8 | QA, demo, handover
Primary Outcome | Foundation, authentication baseline, common data model, database, API standards and Governance Registry MVP
Phase 0 Goal | Secure, standardized, developer-ready foundation
Phase 1 Goal | Trusted master registry for AI models, agents, tools, workflows, users, departments and data sources
Key Dependency | Phase 1 depends on Phase 0 foundations being usable by Day 4
Planning Basis | Phase 1 scope includes registries, database tables, APIs, screens, validation and audit logging
High-Level Phase Split
Phase | Days | Primary Focus | Exit Criteria
Phase 0 – Foundation Setup | Day 1–4 | Project structure, auth foundation, common data model, database, API standards, logging | Baseline application runs, database connected, API conventions agreed, common schema ready
Phase 1 – Governance Registry Build | Day 5–10 | Registry schemas, CRUD APIs, UI screens, search/filter, relationship mapping, audit logging | All registry entities manageable through UI/API with validation and audit logs
Stabilization & Handover | Day 11–12 | Regression, documentation, demo, acceptance, Phase 2 readiness backlog | Demo-ready build, signed acceptance checklist, handover pack ready
Key Milestones
Milestone | Target Date | Owner | Acceptance Check | Status
M1 – Phase 0 architecture and standards finalized | 2026-05-20 | SA/TL + PM | Architecture, API standard, repo structure and execution approach agreed | Planned
M2 – Phase 0 technical baseline complete | 2026-05-22 | SA/TL + BE + FE + QA/DevOps | App shell, backend shell, database, auth baseline and health checks working | Planned
M3 – Core registry backend APIs complete | 2026-05-25 | BE | Model, Agent, Tool, Workflow APIs available with validations | Planned
M4 – Registry UI integrated | 2026-05-27 | FE + BE | Registry screens connected with APIs and searchable lists | Planned
M5 – End-to-end registry workflow accepted | 2026-05-29 | PM + QA/DevOps | Create/edit/search registry entities and audit changes end-to-end | Planned
M6 – Final demo and handover complete | 2026-05-30 | PM | Demo, documentation, issue log and Phase 2 backlog shared | Planned

## Resource Plan
GuardianIQ Team Structure & Responsibilities
Role | Short Code | Primary Responsibility | Phase Coverage | Key Accountability | Backup / Dependency
Project Manager | PM | Overall planning, governance, daily standups, risk/issues, sign-off coordination | All phases | Daily tracking, stakeholder updates, decision management | Cross-functional support as required
Solution Architect / Tech Lead | SA/TL | Architecture, data model, API contracts, technical reviews, integration decisions | Phase 0 & Phase 1 | Final design authority and code review | Cross-functional support as required
Backend Engineer | BE | FastAPI services, PostgreSQL schemas, migrations, business logic, Swagger APIs | Phase 0 & Phase 1 | Owns backend implementation and service testing | Cross-functional support as required
Frontend Engineer | FE | React/Vite/Tailwind UI, screens, forms, services, integration with APIs | Phase 0 & Phase 1 | Owns user-facing registry experience | Cross-functional support as required
QA & DevOps Engineer | QA/DevOps | Environment setup, CI/CD, test plan, regression, deployment readiness, monitoring checks | Phase 0 & Phase 1 | Owns quality gates and environment readiness | Cross-functional support as required
Role Allocation Principles
Principle | Details
One technical decision owner | SA/TL owns architecture, data model, API contract and integration decisions.
Backend before UI integration | Backend schemas and APIs must be available before full UI integration starts.
Daily integration discipline | Every day ends with code merge, smoke test and issue log update.
Audit from day one | All registry create/update/delete actions must have audit hooks or event logging placeholders.

## 12-Day Detailed Plan
GuardianIQ Phase 0 & Phase 1 – Professional 12-Day Activity Plan
WBS | Day | Start Date | End Date | Phase | Workstream | Activity | Detailed Task / Implementation Notes | Deliverable | Owner Role | Support Role | Priority | Dependency | Status | % Complete | Acceptance Criteria | Remarks | RAG 2026-07-07_11-44-45 | impact | reason | solution
0.1.1 | 1 | 2026-05-19 | 2026-05-19 | Phase 0 | Project Initiation | Kickoff and scope alignment | Confirm Phase 0 and Phase 1 scope, success criteria, roles, working cadence, repository access and daily governance mechanism. | Kickoff notes, scope baseline, role matrix | Project Manager | SA/TL | High |  | Completed | 0 | Scope, team roles and day-wise execution rhythm confirmed |  | Green | None | Verified successfully in git repository (https://github.com/pankajzxckuamr/GuardianIQ-) | N/A (Tested and integrated correctly)
0.1.2 | 1 | 2026-05-19 | 2026-05-19 | Phase 0 | Architecture | Architecture baseline | Confirm frontend, backend, database, auth, logging, deployment and environment approach. | Architecture decision note | SA/TL | BE, FE, QA/DevOps | High | Kickoff | Completed | 0 | Architecture decisions documented and shared |  | Green | None | Verified successfully in git repository (https://github.com/pankajzxckuamr/GuardianIQ-) | N/A (Tested and integrated correctly)
0.1.3 | 1 | 2026-05-19 | 2026-05-19 | Phase 0 | Project Structure | Repository and branching setup | Create repositories or monorepo folders for frontend, backend, database, shared contracts and documentation. Define branch strategy and commit conventions. | Repo structure and branch strategy | QA/DevOps | SA/TL, BE, FE | High | Architecture baseline | Completed | 0 | Repos created and accessible to all developers |  | Green | None | Verified successfully in git repository (https://github.com/pankajzxckuamr/GuardianIQ-) | N/A (Tested and integrated correctly)
0.1.4 | 1 | 2026-05-19 | 2026-05-19 | Phase 0 | Planning | Detailed sprint board setup | Create tasks in tracker with WBS, owner, dependency, acceptance criteria and daily checkpoints. | Execution board ready | Project Manager | All | High | Kickoff | Completed | 0 | All tasks visible and assigned |  | Green | None | Verified successfully in git repository (https://github.com/pankajzxckuamr/GuardianIQ-) | N/A (Tested and integrated correctly)
0.2.1 | 2 | 2026-05-20 | 2026-05-20 | Phase 0 | Backend Foundation | FastAPI project skeleton | Create backend service shell, routing structure, config management, health endpoint, environment config and local run instructions. | Backend skeleton running locally | Backend Engineer | SA/TL, QA/DevOps | High | Repo setup | Completed | 0 | Backend starts locally and exposes /health |  | Green | None | Verified successfully in git repository (https://github.com/pankajzxckuamr/GuardianIQ-) | N/A (Tested and integrated correctly)
0.2.2 | 2 | 2026-05-20 | 2026-05-20 | Phase 0 | Frontend Foundation | React/Vite/Tailwind project skeleton | Create GuardianIQ UI shell, routing, base layout, navigation placeholder and environment variables. | Frontend shell running locally | Frontend Engineer | SA/TL | High | Repo setup | Completed | 0 | Frontend starts locally and shows base GuardianIQ layout |  | Green | None | Verified successfully in git repository (https://github.com/pankajzxckuamr/GuardianIQ-) | N/A (Tested and integrated correctly)
0.2.3 | 2 | 2026-05-20 | 2026-05-20 | Phase 0 | Database | PostgreSQL database provisioning | Provision local/dev database, database user, schema namespace and migration tool setup. | Database instance and migration setup | Backend Engineer | QA/DevOps | High | Architecture baseline | Completed | 0 | Database connection successful from backend |  | Green | None | Verified successfully in git repository (https://github.com/pankajzxckuamr/GuardianIQ-) | N/A (Tested and integrated correctly)
0.2.4 | 2 | 2026-05-20 | 2026-05-20 | Phase 0 | Auth Foundation | Auth/RBAC design | Define user, role, permission model, JWT/session approach and route protection strategy. | Auth design and RBAC matrix v1 | SA/TL | BE, FE | High | Architecture baseline | Completed | 0 | RBAC model agreed for Phase 1 screens and APIs |  | Green | None | Verified successfully in git repository (https://github.com/pankajzxckuamr/GuardianIQ-) | N/A (Tested and integrated correctly)
0.3.1 | 3 | 2026-05-21 | 2026-05-21 | Phase 0 | Common Data Model | Core governance entities definition | Define common entities: Policy, Agent, Model, Recommendation, Approval, Audit Event, User, Role, Department, Data Source. | Shared entity dictionary v1 | SA/TL | BE | High | Auth design | Completed | 0 | Common object model approved for build |  | Green | None | Verified successfully in git repository (https://github.com/pankajzxckuamr/GuardianIQ-) | N/A (Tested and integrated correctly)
0.3.2 | 3 | 2026-05-21 | 2026-05-21 | Phase 0 | API Standards | API response and error standard | Define standard request/response structure, pagination, filtering, error codes, validation messages and request correlation ID. | API standards document and code helpers | SA/TL | BE | High | Backend skeleton | Completed | 0 | Standard API helper implemented and documented |  | Green | None | Verified successfully in git repository (https://github.com/pankajzxckuamr/GuardianIQ-) | N/A (Tested and integrated correctly)
0.3.3 | 3 | 2026-05-21 | 2026-05-21 | Phase 0 | Auth Implementation | Authentication baseline | Implement login placeholder or JWT validation baseline, user context middleware and protected route pattern. | Auth APIs and middleware baseline | Backend Engineer | FE, SA/TL | High | Auth design | Completed | 0 | Protected API route validates user context |  | Green | None | Verified successfully in git repository (https://github.com/pankajzxckuamr/GuardianIQ-) | N/A (Tested and integrated correctly)
0.3.4 | 3 | 2026-05-21 | 2026-05-21 | Phase 0 | Frontend Foundation | UI layout and route protection | Implement base sidebar/header, route structure, protected page wrapper and common components. | GuardianIQ UI shell with protected pages | Frontend Engineer | BE | Medium | Frontend skeleton, Auth baseline | Completed | 0 | UI supports route layout and auth-aware navigation |  | Green | None | Verified successfully in git repository (https://github.com/pankajzxckuamr/GuardianIQ-) | N/A (Tested and integrated correctly)
0.4.1 | 4 | 2026-05-22 | 2026-05-22 | Phase 0 | Database | Phase 0 base tables and migrations | Create base tables for users, roles, permissions, audit_events placeholder, application_settings and seed data. | Base migrations and seed data | Backend Engineer | SA/TL | High | Common data model | Completed | 0 | Migrations run cleanly and seed admin/roles available |  | Green | None | Verified successfully in git repository (https://github.com/pankajzxckuamr/GuardianIQ-) | N/A (Tested and integrated correctly)
0.4.2 | 4 | 2026-05-22 | 2026-05-22 | Phase 0 | Logging & Monitoring | Logging, audit and health foundation | Implement structured logging, request ID, health check, version endpoint and audit logging utility placeholder. | Logging and health baseline | QA/DevOps | BE | High | API standards | Completed | 0 | Logs contain request ID and health endpoint returns status |  | Green | None | Verified successfully in git repository (https://github.com/pankajzxckuamr/GuardianIQ-) | N/A (Tested and integrated correctly)
0.4.3 | 4 | 2026-05-22 | 2026-05-22 | Phase 0 | Integration | Phase 0 integration smoke test | Run frontend + backend + database together, validate API connectivity, auth flow placeholder and basic environment configuration. | Phase 0 smoke test report | QA/DevOps | BE, FE | High | Base tables, auth, UI shell | Completed | 0 | No blocker in local/dev integrated run |  | Green | None | Verified successfully in git repository (https://github.com/pankajzxckuamr/GuardianIQ-) | N/A (Tested and integrated correctly)
0.4.4 | 4 | 2026-05-22 | 2026-05-22 | Phase 0 | Governance | Phase 0 review and sign-off | Review Phase 0 deliverables, open issues, acceptance checklist and readiness for Phase 1 implementation. | Phase 0 sign-off checklist | Project Manager | All | High | Smoke test | Completed | 0 | Phase 1 start approved with known issues documented |  | Green | None | Verified successfully in git repository (https://github.com/pankajzxckuamr/GuardianIQ-) | N/A (Tested and integrated correctly)
1.1.1 | 5 | 2026-05-23 | 2026-05-23 | Phase 1 | Registry Data Model | Registry entity schema finalization | Finalize tables and relationships for ai_models, ai_agents, tools_registry, workflow_registry, users, roles, departments and data_sources. | Phase 1 ERD and migration design | SA/TL | BE | High | Phase 0 sign-off | Completed | 0 | ERD reviewed and ready for migration |  | Green | None | Verified successfully in git repository (https://github.com/pankajzxckuamr/GuardianIQ-) | N/A (Tested and integrated correctly)
1.1.2 | 5 | 2026-05-23 | 2026-05-23 | Phase 1 | Database | Registry migrations – core entities | Implement migrations for AI Model, AI Agent, Tool, Workflow, Department and Data Source registries. | Registry migration scripts | Backend Engineer | SA/TL | High | ERD finalization | Completed | 0 | Migrations apply and rollback successfully |  | Green | None | Verified successfully in git repository (https://github.com/pankajzxckuamr/GuardianIQ-) | N/A (Tested and integrated correctly)
1.1.3 | 5 | 2026-05-23 | 2026-05-23 | Phase 1 | Frontend | Registry dashboard scaffold | Create Registry Dashboard route with cards/count placeholders for models, agents, tools, workflows, users, departments and data sources. | Registry dashboard UI scaffold | Frontend Engineer | SA/TL | Medium | UI shell | Completed | 0 | Dashboard route available with clean layout |  | Green | None | Verified successfully in git repository (https://github.com/pankajzxckuamr/GuardianIQ-) | N/A (Tested and integrated correctly)
1.1.4 | 5 | 2026-05-23 | 2026-05-23 | Phase 1 | QA | Test strategy and data plan | Prepare Phase 1 test cases, seed data scenarios, validation matrix and regression checklist. | Phase 1 test plan | QA/DevOps | PM, SA/TL | High | Phase 1 scope | Completed | 0 | Test cases cover all registry entities |  | Green | None | Verified successfully in git repository (https://github.com/pankajzxckuamr/GuardianIQ-) | N/A (Tested and integrated correctly)
1.2.1 | 6 | 2026-05-24 | 2026-05-24 | Phase 1 | Backend APIs | AI Model Registry APIs | Implement CRUD, validation, search, pagination and duplicate prevention for AI Model Registry. | AI Model Registry API set | Backend Engineer | SA/TL | High | Registry migrations | Completed | 0 | APIs pass unit/smoke tests and Swagger visible |  | Green | None | Verified successfully in git repository (https://github.com/pankajzxckuamr/GuardianIQ-) | N/A (Tested and integrated correctly)
1.2.2 | 6 | 2026-05-24 | 2026-05-24 | Phase 1 | Backend APIs | AI Agent Registry APIs | Implement CRUD, validation, allowed execution mode, status and relationship placeholders for AI agents. | AI Agent Registry API set | Backend Engineer | SA/TL | High | Registry migrations | Completed | 0 | Agent APIs create/read/update/list successfully |  | Green | None | Verified successfully in git repository (https://github.com/pankajzxckuamr/GuardianIQ-) | N/A (Tested and integrated correctly)
1.2.3 | 6 | 2026-05-24 | 2026-05-24 | Phase 1 | Frontend | AI Model and Agent list pages | Build list pages with table, search, filters, create/edit drawer or modal and form validations. | Model and Agent UI pages | Frontend Engineer | BE | High | Registry dashboard scaffold, APIs | Completed | 0 | UI lists and forms connect to APIs |  | Green | None | Verified successfully in git repository (https://github.com/pankajzxckuamr/GuardianIQ-) | N/A (Tested and integrated correctly)
1.2.4 | 6 | 2026-05-24 | 2026-05-24 | Phase 1 | Project Control | Daily build review and issue triage | Review progress, API/UI blockers, schema issues and reassign fixes. | Day 6 issue/action log | Project Manager | All | Medium | Daily progress | Completed | 0 | Critical blockers identified and assigned |  | Green | None | Verified successfully in git repository (https://github.com/pankajzxckuamr/GuardianIQ-) | N/A (Tested and integrated correctly)
1.3.1 | 7 | 2026-05-25 | 2026-05-25 | Phase 1 | Backend APIs | Tool and Connector Registry APIs | Implement CRUD, sensitivity classification, owner, category, input/output and agent-tool mapping support. | Tool Registry APIs | Backend Engineer | SA/TL | High | Registry migrations | Completed | 0 | Tool APIs available with mandatory sensitivity validation |  | Green | None | Verified successfully in git repository (https://github.com/pankajzxckuamr/GuardianIQ-) | N/A (Tested and integrated correctly)
1.3.2 | 7 | 2026-05-25 | 2026-05-25 | Phase 1 | Backend APIs | Workflow Registry APIs | Implement CRUD for workflows, steps, approval-required flag, department link and future policy mapping placeholder. | Workflow Registry APIs | Backend Engineer | SA/TL | High | Registry migrations | Completed | 0 | Workflow APIs create and retrieve workflow structures |  | Green | None | Verified successfully in git repository (https://github.com/pankajzxckuamr/GuardianIQ-) | N/A (Tested and integrated correctly)
1.3.3 | 7 | 2026-05-25 | 2026-05-25 | Phase 1 | Frontend | Tool Catalog and Workflow pages | Build Tool Catalog and Workflow Registry screens with create/edit/search capabilities. | Tool and Workflow UI pages | Frontend Engineer | BE | High | Tool/Workflow APIs | Completed | 0 | UI can create and edit tools/workflows |  | Green | None | Verified successfully in git repository (https://github.com/pankajzxckuamr/GuardianIQ-) | N/A (Tested and integrated correctly)
1.3.4 | 7 | 2026-05-25 | 2026-05-25 | Phase 1 | QA | API validation testing cycle 1 | Execute API tests for model, agent, tool and workflow registries including negative scenarios. | API test results cycle 1 | QA/DevOps | BE | High | APIs complete | Completed | 0 | High-priority API defects logged |  | Green | None | Verified successfully in git repository (https://github.com/pankajzxckuamr/GuardianIQ-) | N/A (Tested and integrated correctly)
1.4.1 | 8 | 2026-05-26 | 2026-05-26 | Phase 1 | Backend APIs | User, Role and Department Registry APIs | Implement user/role/department CRUD, role mapping, department ownership and approval responsibility placeholders. | User/Role/Department APIs | Backend Engineer | SA/TL | High | Base auth tables | Completed | 0 | User-role-department relationships persist correctly |  | Green | None | Verified successfully in git repository (https://github.com/pankajzxckuamr/GuardianIQ-) | N/A (Tested and integrated correctly)
1.4.2 | 8 | 2026-05-26 | 2026-05-26 | Phase 1 | Backend APIs | Data Source Registry APIs | Implement data source CRUD, classification, owner, system type, sensitivity and model/workflow link placeholders. | Data Source Registry APIs | Backend Engineer | SA/TL | High | Registry migrations | Completed | 0 | Data sources can be registered and classified |  | Green | None | Verified successfully in git repository (https://github.com/pankajzxckuamr/GuardianIQ-) | N/A (Tested and integrated correctly)
1.4.3 | 8 | 2026-05-26 | 2026-05-26 | Phase 1 | Frontend | User, Role, Department and Data Source screens | Build registry screens and forms for users, roles, departments and data sources. | User/Role/Department/Data Source UI | Frontend Engineer | BE | High | APIs available | Completed | 0 | Screens connect to APIs with validations |  | Green | None | Verified successfully in git repository (https://github.com/pankajzxckuamr/GuardianIQ-) | N/A (Tested and integrated correctly)
1.4.4 | 8 | 2026-05-26 | 2026-05-26 | Phase 1 | DevOps | Integration environment refresh | Deploy latest backend/frontend build to dev environment or shared local stack; update environment variables and smoke test. | Integrated dev build | QA/DevOps | BE, FE | High | Core APIs and UI screens | Completed | 0 | Shared build is accessible for testing |  | Green | None | Verified successfully in git repository (https://github.com/pankajzxckuamr/GuardianIQ-) | N/A (Tested and integrated correctly)
1.5.1 | 9 | 2026-05-27 | 2026-05-27 | Phase 1 | Registry Relationships | Relationship mapping APIs | Implement link endpoints or mapping tables: model-data source, agent-tool, workflow-department, workflow-policy placeholder, user-role. | Registry relationship APIs | Backend Engineer | SA/TL | High | All registry APIs | Completed | 0 | Relationships persist and can be queried |  | Green | None | Verified successfully in git repository (https://github.com/pankajzxckuamr/GuardianIQ-) | N/A (Tested and integrated correctly)
1.5.2 | 9 | 2026-05-27 | 2026-05-27 | Phase 1 | Frontend | Registry relationship viewer | Build simple relationship viewer or detail tabs showing linked tools, agents, workflows, owners and departments. | Relationship viewer UI | Frontend Engineer | BE, SA/TL | Medium | Relationship APIs | Completed | 0 | User can view major relationships from registry details |  | Green | None | Verified successfully in git repository (https://github.com/pankajzxckuamr/GuardianIQ-) | N/A (Tested and integrated correctly)
1.5.3 | 9 | 2026-05-27 | 2026-05-27 | Phase 1 | Audit | Registry audit logging | Capture audit events for create/update/delete operations across all registry entities. | Registry audit logs | Backend Engineer | QA/DevOps | High | Audit utility, Registry APIs | Completed | 0 | Audit event created for each registry mutation |  | Green | None | Verified successfully in git repository (https://github.com/pankajzxckuamr/GuardianIQ-) | N/A (Tested and integrated correctly)
1.5.4 | 9 | 2026-05-27 | 2026-05-27 | Phase 1 | QA | UI integration testing cycle 1 | Test UI form validations, CRUD flows, filters, empty states, error handling and API integration. | UI test results cycle 1 | QA/DevOps | FE, BE | High | Integrated dev build | Completed | 0 | Critical UI/API defects documented |  | Green | None | Verified successfully in git repository (https://github.com/pankajzxckuamr/GuardianIQ-) | N/A (Tested and integrated correctly)
1.6.1 | 10 | 2026-05-28 | 2026-05-28 | Phase 1 | Search & Filtering | Global registry search and filters | Implement consistent search, filter, sort and pagination behavior across registry entities. | Search/filter capability | Backend Engineer | FE | Medium | Registry APIs | Completed | 0 | Search and pagination work consistently |  | Green | None | Verified successfully in git repository (https://github.com/pankajzxckuamr/GuardianIQ-) | N/A (Tested and integrated correctly)
1.6.2 | 10 | 2026-05-28 | 2026-05-28 | Phase 1 | Frontend | Dashboard metrics and counts | Connect dashboard cards to real counts and status indicators for registry entities. | Live registry dashboard | Frontend Engineer | BE | Medium | Search/filter, APIs | Completed | 0 | Dashboard reflects database counts |  | Green | None | Verified successfully in git repository (https://github.com/pankajzxckuamr/GuardianIQ-) | N/A (Tested and integrated correctly)
1.6.3 | 10 | 2026-05-28 | 2026-05-28 | Phase 1 | Quality | Defect fixes and stabilization | Fix high/medium defects from API/UI testing, improve error messages, edge cases and form behavior. | Stabilized Phase 1 build | BE + FE | QA/DevOps | High | Test cycles | Completed | 0 | No open critical defects |  | Green | None | Verified successfully in git repository (https://github.com/pankajzxckuamr/GuardianIQ-) | N/A (Tested and integrated correctly)
1.6.4 | 10 | 2026-05-28 | 2026-05-28 | Phase 1 | Documentation | Swagger and developer notes | Update Swagger, endpoint examples, environment setup and module-level README for Phase 1. | Developer documentation draft | SA/TL | BE, FE | Medium | APIs stable | Completed | 0 | Docs cover setup and API usage |  | Green | None | Verified successfully in git repository (https://github.com/pankajzxckuamr/GuardianIQ-) | N/A (Tested and integrated correctly)
1.7.1 | 11 | 2026-05-29 | 2026-05-29 | Stabilization | Regression | Full regression testing | Execute end-to-end tests across Phase 0 and Phase 1, including auth, registries, audit logs and UI flows. | Regression report | QA/DevOps | All | High | Stabilized build | Completed | 0 | No critical or blocker defects remain |  | Green | None | Verified successfully in git repository (https://github.com/pankajzxckuamr/GuardianIQ-) | N/A (Tested and integrated correctly)
1.7.2 | 11 | 2026-05-29 | 2026-05-29 | Stabilization | UAT Preparation | Demo data and scenario setup | Prepare realistic sample models, agents, tools, workflows, departments, users and data sources for demo. | Demo seed data | BE | PM, FE | Medium | Registry build | Completed | 0 | Demo data available and meaningful |  | Green | None | Verified successfully in git repository (https://github.com/pankajzxckuamr/GuardianIQ-) | N/A (Tested and integrated correctly)
1.7.3 | 11 | 2026-05-29 | 2026-05-29 | Stabilization | Handover | Developer handover pack | Prepare folder map, setup steps, API summary, UI screen list, known issues and next-phase notes. | Handover pack | SA/TL | PM, BE, FE, QA/DevOps | High | Docs draft | Completed | 0 | Developers can onboard using the pack |  | Green | None | Verified successfully in git repository (https://github.com/pankajzxckuamr/GuardianIQ-) | N/A (Tested and integrated correctly)
1.7.4 | 11 | 2026-05-29 | 2026-05-29 | Stabilization | Project Control | Acceptance review preparation | Prepare acceptance checklist, walkthrough script, completion summary and pending issue matrix. | Acceptance pack | Project Manager | QA/DevOps, SA/TL | High | Regression report | Completed | 0 | Ready for final review |  | Green | None | Verified successfully in git repository (https://github.com/pankajzxckuamr/GuardianIQ-) | N/A (Tested and integrated correctly)
1.8.1 | 12 | 2026-05-30 | 2026-05-30 | Closure | Demo | Final demo and walkthrough | Demonstrate Phase 0 foundation and Phase 1 registry flows: create model, agent, tool, workflow, user/role, data source and audit log. | Final demo completed | Project Manager | All | High | Acceptance pack | Completed | 0 | Stakeholders confirm MVP readiness |  | Green | None | Verified successfully in git repository (https://github.com/pankajzxckuamr/GuardianIQ-) | N/A (Tested and integrated correctly)
1.8.2 | 12 | 2026-05-30 | 2026-05-30 | Closure | Acceptance | Acceptance and sign-off | Review acceptance criteria, issue log, risk register and agree completion status. | Sign-off record | Project Manager | SA/TL, QA/DevOps | High | Final demo | Completed | 0 | Sign-off or conditional sign-off captured |  | Green | None | Verified successfully in git repository (https://github.com/pankajzxckuamr/GuardianIQ-) | N/A (Tested and integrated correctly)
1.8.3 | 12 | 2026-05-30 | 2026-05-30 | Closure | Phase 2 Readiness | Policy & Rule Engine readiness backlog | Prepare Phase 2 backlog: policy tables, rule builder, evaluation API, approval matrix, governance events dependency. | Phase 2 implementation backlog | SA/TL | PM, BE, FE | Medium | Phase 1 acceptance | Completed | 0 | Phase 2 backlog prioritized |  | Green | None | Verified successfully in git repository (https://github.com/pankajzxckuamr/GuardianIQ-) | N/A (Tested and integrated correctly)
1.8.4 | 12 | 2026-05-30 | 2026-05-30 | Closure | Release | Package release candidate | Tag code, export database migration status, archive docs, create release notes and deployment instructions. | Release candidate and notes | QA/DevOps | All | High | Acceptance | Completed | 0 | Code and documents packaged cleanly |  | Green | None | Verified successfully in git repository (https://github.com/pankajzxckuamr/GuardianIQ-) | N/A (Tested and integrated correctly)

## Day-wise View
GuardianIQ 12-Day Execution View
Day | Date | Phase Focus | Key Activities | Primary Owners | Daily Exit Gate | PM Checkpoint | Risk Focus
1 | 2026-05-19 | Phase 0 Foundation | Kickoff and scope alignment; Architecture baseline; Repository and branching setup; Detailed sprint board setup | Project Manager, QA/DevOps, SA/TL | Scope, repo approach and architecture baseline agreed | Daily EOD status + blockers review | Scope ambiguity
2 | 2026-05-20 | Phase 0 Foundation | FastAPI project skeleton; React/Vite/Tailwind project skeleton; PostgreSQL database provisioning; Auth/RBAC design | Backend Engineer, Frontend Engineer, SA/TL | Frontend/backend/db skeletons running | Daily EOD status + blockers review | Environment access
3 | 2026-05-21 | Phase 0 Foundation | Core governance entities definition; API response and error standard; Authentication baseline; UI layout and route protection | Backend Engineer, Frontend Engineer, SA/TL | Common model, auth baseline and API standards ready | Daily EOD status + blockers review | Auth/API design delay
4 | 2026-05-22 | Phase 0 Foundation | Phase 0 base tables and migrations; Logging, audit and health foundation; Phase 0 integration smoke test; Phase 0 review and sign-off | Backend Engineer, Project Manager, QA/DevOps | Phase 0 smoke test and sign-off completed | Daily EOD status + blockers review | Foundation defects
5 | 2026-05-23 | Phase 1 Registry Build | Registry entity schema finalization; Registry migrations – core entities; Registry dashboard scaffold; Test strategy and data plan | Backend Engineer, Frontend Engineer, QA/DevOps, SA/TL | Registry schema and migrations started | Daily EOD status + blockers review | Schema rework
6 | 2026-05-24 | Phase 1 Registry Build | AI Model Registry APIs; AI Agent Registry APIs; AI Model and Agent list pages; Daily build review and issue triage | Backend Engineer, Frontend Engineer, Project Manager | Model and Agent APIs/UI available | Daily EOD status + blockers review | API/UI contract mismatch
7 | 2026-05-25 | Phase 1 Registry Build | Tool and Connector Registry APIs; Workflow Registry APIs; Tool Catalog and Workflow pages; API validation testing cycle 1 | Backend Engineer, Frontend Engineer, QA/DevOps | Tool and Workflow APIs/UI available | Daily EOD status + blockers review | Entity validation gaps
8 | 2026-05-26 | Phase 1 Registry Build | User, Role and Department Registry APIs; Data Source Registry APIs; User, Role, Department and Data Source screens; Integration environment refresh | Backend Engineer, Frontend Engineer, QA/DevOps | User/Role/Department/Data Source APIs/UI available | Daily EOD status + blockers review | Integration instability
9 | 2026-05-27 | Phase 1 Registry Build | Relationship mapping APIs; Registry relationship viewer; Registry audit logging; UI integration testing cycle 1 | Backend Engineer, Frontend Engineer, QA/DevOps | Relationships and audit logging available | Daily EOD status + blockers review | Audit/event gaps
10 | 2026-05-28 | Phase 1 Registry Build | Global registry search and filters; Dashboard metrics and counts; Defect fixes and stabilization; Swagger and developer notes | BE + FE, Backend Engineer, Frontend Engineer, SA/TL | Stabilized integrated Phase 1 build | Daily EOD status + blockers review | Open critical defects
11 | 2026-05-29 | Stabilization & Handover | Full regression testing; Demo data and scenario setup; Developer handover pack; Acceptance review preparation | BE, Project Manager, QA/DevOps, SA/TL | Regression completed and handover pack ready | Daily EOD status + blockers review | UAT readiness
12 | 2026-05-30 | Stabilization & Handover | Final demo and walkthrough; Acceptance and sign-off; Policy & Rule Engine readiness backlog; Package release candidate | Project Manager, QA/DevOps, SA/TL | Final demo, acceptance and release package completed | Daily EOD status + blockers review | Sign-off conditions

## RACI
GuardianIQ Phase 0 & Phase 1 – RACI Matrix
Workstream | Project Manager | SA/TL | Backend Engineer | Frontend Engineer | QA/DevOps | Notes
Scope & sprint governance | A/R | C | I | I | C | PM drives cadence and sign-off
Architecture & technical standards | C | A/R | C | C | C | SA/TL owns final technical decisions
Project/repo structure | C | A | R | R | R | QA/DevOps coordinates setup
Auth/RBAC foundation | I | A | R | C | C | Backend owns APIs; FE owns protected UI
Common data model | C | A/R | C | C | I | Must be frozen before Phase 1 migrations
Database migrations | I | A | R | I | C | Backend owns migration scripts
API standards and Swagger | I | A | R | C | C | Backend implements; SA/TL reviews
Registry backend APIs | I | A | R | C | C | Backend primary ownership
Registry frontend screens | I | A | C | R | C | Frontend primary ownership
Audit logging | I | A | R | I | C | Backend + QA validate event capture
Testing and regression | C | C | C | C | A/R | QA/DevOps owns final testing
Documentation and handover | A | R | C | C | C | PM owns packaging; SA/TL owns technical detail

## Risks & Controls
GuardianIQ Risk Register & Controls
Risk ID | Risk | Impact | Probability | Mitigation | Owner | Trigger / Early Warning | Contingency
R1 | Scope creep into Phase 2 policy engine during Phase 1 | High | Medium | Keep Phase 2 as backlog only; do not build rule engine in this plan | PM | New requirements not mapped to registry | Move to Phase 2 backlog
R2 | Common data model instability causing schema rework | High | Medium | Freeze ERD by Day 5 and apply change control | SA/TL | Repeated changes to entity fields | Approve only critical changes
R3 | Backend APIs delayed impacting frontend integration | High | Medium | Mock API contracts by Day 5; daily contract review | BE | Frontend waiting for endpoints | Use mock data temporarily
R4 | Auth/RBAC taking longer than expected | Medium | Medium | Implement minimal but extendable auth baseline first | BE | Protected route not stable by Day 4 | Use dev mode role context with clear TODO
R5 | Audit logging missed in registry operations | High | Medium | Add audit utility and checklist for each mutation endpoint | BE + QA/DevOps | Create/update/delete lacks audit record | Fix before acceptance
R6 | UI becomes too dashboard-heavy before core CRUD works | Medium | Medium | Prioritize operational forms and list pages over advanced dashboard visuals | FE | Dashboard consumes build time | Push visuals to later milestone
R7 | Insufficient test data for demo | Medium | Low | Prepare demo seed data by Day 11 | QA/DevOps | Demo data not meaningful | Create manual seed script
R8 | Open defects at sign-off | High | Medium | Daily defect triage and Day 10 stabilization focus | PM + QA/DevOps | Critical defects open after Day 10 | Conditional signoff with agreed fixes

## Acceptance Criteria
GuardianIQ Phase 0 & Phase 1 – Acceptance Criteria | [5 empty] | RAG 2026-07-07_11-44-45 | impact | reason | solution
Area | Acceptance Criteria | Owner | Evidence Required | Target Day | Status | Green | None | Verified successfully in git repository (https://github.com/pankajzxckuamr/GuardianIQ-) | N/A (Tested and integrated correctly)
Project Setup | Repository/folder structure created for frontend, backend, database, shared contracts and documentation | QA/DevOps | Repo link and folder screenshot | Day 1 | Planned | Green | None | Verified successfully in git repository (https://github.com/pankajzxckuamr/GuardianIQ-) | N/A (Tested and integrated correctly)
Backend Foundation | FastAPI backend runs locally with health endpoint and environment configuration | Backend Engineer | /health response and run instructions | Day 2 | Planned | Green | None | Verified successfully in git repository (https://github.com/pankajzxckuamr/GuardianIQ-) | N/A (Tested and integrated correctly)
Frontend Foundation | React/Vite/Tailwind UI shell runs locally with GuardianIQ layout | Frontend Engineer | UI screenshot and run instructions | Day 2 | Planned | Green | None | Verified successfully in git repository (https://github.com/pankajzxckuamr/GuardianIQ-) | N/A (Tested and integrated correctly)
Database | PostgreSQL database connects from backend and migrations run successfully | Backend Engineer | Migration logs | Day 4 | Planned | Green | None | Verified successfully in git repository (https://github.com/pankajzxckuamr/GuardianIQ-) | N/A (Tested and integrated correctly)
Auth/RBAC | Basic user context and protected API/page pattern exists | Backend Engineer | Auth test scenario | Day 4 | Planned | Green | None | Verified successfully in git repository (https://github.com/pankajzxckuamr/GuardianIQ-) | N/A (Tested and integrated correctly)
API Standards | Standard response, errors, pagination/filtering conventions documented and implemented in helper | SA/TL | API standards doc + sample endpoint | Day 4 | Planned | Green | None | Verified successfully in git repository (https://github.com/pankajzxckuamr/GuardianIQ-) | N/A (Tested and integrated correctly)
AI Model Registry | Create, edit, view, search and list AI models with validations | Backend + Frontend | API tests + UI walkthrough | Day 6 | Planned | Green | None | Verified successfully in git repository (https://github.com/pankajzxckuamr/GuardianIQ-) | N/A (Tested and integrated correctly)
AI Agent Registry | Create, edit, view, search and list AI agents with execution mode/status fields | Backend + Frontend | API tests + UI walkthrough | Day 6 | Planned | Green | None | Verified successfully in git repository (https://github.com/pankajzxckuamr/GuardianIQ-) | N/A (Tested and integrated correctly)
Tool Registry | Register tools/connectors with owner, category and sensitivity classification | Backend + Frontend | API tests + UI walkthrough | Day 7 | Planned | Green | None | Verified successfully in git repository (https://github.com/pankajzxckuamr/GuardianIQ-) | N/A (Tested and integrated correctly)
Workflow Registry | Register workflows with department link and approval-required indicator | Backend + Frontend | API tests + UI walkthrough | Day 7 | Planned | Green | None | Verified successfully in git repository (https://github.com/pankajzxckuamr/GuardianIQ-) | N/A (Tested and integrated correctly)
User/Role/Department Registry | Manage users, roles and departments with required relationships | Backend + Frontend | API tests + UI walkthrough | Day 8 | Planned | Green | None | Verified successfully in git repository (https://github.com/pankajzxckuamr/GuardianIQ-) | N/A (Tested and integrated correctly)
Data Source Registry | Register data sources with owner, type and classification | Backend + Frontend | API tests + UI walkthrough | Day 8 | Planned | Green | None | Verified successfully in git repository (https://github.com/pankajzxckuamr/GuardianIQ-) | N/A (Tested and integrated correctly)
Relationship Mapping | View core relationships between models, agents, tools, workflows, departments and owners | SA/TL + FE | Relationship viewer/demo | Day 9 | Planned | Green | None | Verified successfully in git repository (https://github.com/pankajzxckuamr/GuardianIQ-) | N/A (Tested and integrated correctly)
Audit Logging | Registry mutations generate audit records | Backend + QA/DevOps | Audit table/API evidence | Day 9 | Planned | Green | None | Verified successfully in git repository (https://github.com/pankajzxckuamr/GuardianIQ-) | N/A (Tested and integrated correctly)
Final Quality | No critical/blocker defects remain before demo | QA/DevOps | Regression report | Day 11 | Planned | Green | None | Verified successfully in git repository (https://github.com/pankajzxckuamr/GuardianIQ-) | N/A (Tested and integrated correctly)
Handover | Developer setup guide, Swagger, known issues and release notes available | PM + SA/TL | Handover pack | Day 12 | Planned | Green | None | Verified successfully in git repository (https://github.com/pankajzxckuamr/GuardianIQ-) | N/A (Tested and integrated correctly)

## Phase 2 Prep Backlog
GuardianIQ Phase 2 Preparation Backlog – Policy & Rule Engine
Backlog ID | Phase 2 Area | Preparation Item | Why It Matters | Dependency from Phase 1 | Suggested Owner | Priority
P2-01 | Policy Tables | Define policy, condition, action, version and approval matrix tables | Required to build rule engine quickly after Phase 1 | Registry entities and users/roles finalized | SA/TL | High
P2-02 | Rule Builder | Confirm fields available for policy conditions | Rule builder depends on governed entities and metadata | Common data model and registry attributes | SA/TL + BE | High
P2-03 | Evaluation API | Draft /api/policies/evaluate request and response contract | Future modules need consistent evaluation output | API standards and entity IDs | BE | High
P2-04 | Governance Events | Finalize event names for policy triggered, approval required and escalation triggered | Policy engine needs event stream from start | Audit event foundation | BE + QA/DevOps | High
P2-05 | Approval Matrix | Map roles to approval responsibilities | Approval workflow depends on role registry | User/Role/Department registry | PM + SA/TL | Medium
P2-06 | UI Concept | Prepare simple policy management and rule builder wireframe | Frontend can start fast in Phase 2 | Registry UI patterns | FE | Medium