## Team Task Status n Queries
Day | Start Date | Activity | Remarks | Ayush | Pankaj | Jofrey | Testing Results | Issue Identified | Soultion Suggested | Detailed Task / Implementation Notes | Deliverable | Owner Role | Support Role | Priority | Dependency | Status | % Complete | Acceptance Criteria | End Date | Actual End | Phase | Workstream
1 | 2026-05-19 | Kickoff and scope alignment | All infromations has been shared |  |  | Initial Phase 0 alignment and repository direction reviewed. | PASS |  |  | Confirm Phase 0 and Phase 1 scope, success criteria, roles, working cadence, repository access and daily governance mechanism. | Kickoff notes, scope baseline, role matrix | Project Manager | SA/TL | High | None | Not Started | 0% | Scope, team roles and day-wise execution rhythm confirmed | 2026-05-19 | 2026-05-19 | Phase 0 | Project Initiation
1 | 2026-05-19 | Architecture baseline | All infromations has been shared |  |  | Architecture baseline reviewed and validated against Phase 0 expectations. | PASS |  |  | Confirm frontend, backend, database, auth, logging, deployment and environment approach. | Architecture decision note | SA/TL | BE, FE, QA/DevOps | High | Kickoff | Not Started | 0% | Architecture decisions documented and shared | 2026-05-19 | 2026-05-19 | Phase 0 | Architecture
1 | 2026-05-19 | Repository and branching setup | All infromations has been shared |  | This is the task of 20th and 21st, not on the this particular day. | Repository structure validated. Branch governance partially implemented. | PARTIAL PASS |  | Implement protected develop branch and enforce feature/*, release/*, hotfix/* workflow. | Create repositories or monorepo folders for frontend, backend, database, shared contracts and documentation. Define branch strategy and commit conventions. | Repo structure and branch strategy | QA/DevOps | SA/TL, BE, FE | High | Architecture baseline | Not Started | 0% | Repos created and accessible to all developers | 2026-05-19 | 2026-05-19 | Phase 0 | Project Structure
1 | 2026-05-19 | Detailed sprint board setup | All infromations has been shared |  |  | Sprint tracking artifact available | PASS |  |  | Create tasks in tracker with WBS, owner, dependency, acceptance criteria and daily checkpoints. | Execution board ready | Project Manager | All | High | Kickoff | Not Started | 0% | All tasks visible and assigned | 2026-05-19 | 2026-05-19 | Phase 0 | Planning
2 | 2026-05-20 | FastAPI project skeleton | FastAPI modular backend foundation implemented successfully. | FastAPI foundation, health endpoints | Implemented remaining Auth APIs: /refresh, /logout, /roles, and /permissions.. | Backend skeleton validated including core, db, modules, middleware, and shared components. | PASS |  |  | Create backend service shell, routing structure, config management, health endpoint, environment config and local run instructions. | Backend skeleton running locally | Backend Engineer | SA/TL, QA/DevOps | High | Repo setup | Not Started | 0% | Backend starts locally and exposes /health | 2026-05-20 | 2026-05-20 | Phase 0 | Backend Foundation
2 | 2026-05-20 | React/Vite/Tailwind project skeleton | Frontend foundation exists with Vite/Tailwind setup. |  |  | Frontend skeleton validated with routing/layout/auth structure. | PASS |  |  | Create GuardianIQ UI shell, routing, base layout, navigation placeholder and environment variables. | Frontend shell running locally | Frontend Engineer | SA/TL | High | Repo setup | Not Started | 0% | Frontend starts locally and shows base GuardianIQ layout | 2026-05-20 | 2026-05-27 | Phase 0 | Frontend Foundation
2 | 2026-05-20 | PostgreSQL database provisioning | Alembic and database models exist | Provision database, database user, migration tool setup |  | Database models and migrations validated. | PASS |  | Add dockerized PostgreSQL provisioning and automated setup scripts. | Provision local/dev database, database user, schema namespace and migration tool setup. | Database instance and migration setup | Backend Engineer | QA/DevOps | High | Architecture baseline | Not Started | 0% | Database connection successful from backend | 2026-05-20 | 2026-05-20 | Phase 0 | Database
2 | 2026-05-20 | Auth/RBAC design | JWT auth, permissions, and RBAC dependency structure validated. | defined user | Implemented core RBAC middleware (require_permission) to protect routes based on user permissions. | Authentication and RBAC implementation reviewed successfully. | PASS |  |  | Define user, role, permission model, JWT/session approach and route protection strategy. | Auth design and RBAC matrix v1 | SA/TL | BE, FE | High | Architecture baseline | Not Started | 0% | RBAC model agreed for Phase 1 screens and APIs | 2026-05-20 | 2026-05-20 | Phase 0 | Auth Foundation
3 | 2026-05-21 | Core governance entities definition | Core governance entities are implemented and mapped. | Defined common entities: Policy, Agent, Model, Recommendation, Approval, Audit Event, User, Role, Department, Data Source. Implemented SQLAlchemy models with proper relationships and indexing | Created entities: AIModel, Agent, Recommendation, Approval Defined enums: recommendation_status, approval_status, execution_mode, audit_event_type Integrated all new models into SQLAlchemy Base for Alembic migration readiness Remaining entities (Policy, User, Role, Department, Data Source) scoped and referenced; implementation pending. | Jofrey: Policy, datasource, audit, AI model, agent, approval entities validated. | PASS |  |  | Define common entities: Policy, Agent, Model, Recommendation, Approval, Audit Event, User, Role, Department, Data Source. | Shared entity dictionary v1 | SA/TL | BE | High | Auth design | Not Started | 0% | Common object model approved for build | 2026-05-21 | 2026-05-27 | Phase 0 | Common Data Model
3 | 2026-05-21 | API response and error standard | Standard response structure exists | Implemented pagination, filtering, and sorting across all list endpoints Defined comprehensive error codes | implemented standard request/response structure, validation messages and request correlation ID I am finshed with the Standardization. Centralized middleware and request ID propagation. As this task is mentioned on 22nd may. | API response contract partially validated. | PARTIAL PASS |  | Enforce centralized response wrapper middleware/service across all APIs. | Define standard request/response structure, pagination, filtering, error codes, validation messages and request correlation ID. | API standards document and code helpers | SA/TL | BE | High | Backend skeleton | Not Started | 0% | Standard API helper implemented and documented | 2026-05-21 | 2026-05-27 | Phase 0 | API Standards
3 | 2026-05-21 | Authentication baseline | Access/refresh token auth routes are implemented. | Implemented JWT validation baseline with login placeholder | protected routes, and RBAC middleware are all fully implemented. | Authentication baseline validated including login/refresh/logout endpoints. | PASS | After successful login the user has maximum of 30 mins timeline before backend throws 401 error and redirects user to login screen |  | Implement login placeholder or JWT validation baseline, user context middleware and protected route pattern. | Auth APIs and middleware baseline | Backend Engineer | FE, SA/TL | High | Auth design | Not Started | 0% | Protected API route validates user context | 2026-05-21 | 2026-05-27 | Phase 0 | Auth Implementation
3 | 2026-05-21 | UI layout and route protection | Protected routes and reusable layouts detected. |  |  | Frontend route protection and layout structure validated. | PASS |  |  | Implement base sidebar/header, route structure, protected page wrapper and common components. | GuardianIQ UI shell with protected pages | Frontend Engineer | BE | Medium | Frontend skeleton, Auth baseline | Not Started | 0% | UI supports route layout and auth-aware navigation | 2026-05-21 | 2026-05-27 | Phase 0 | Frontend Foundation
4 | 2026-05-22 | Phase 0 base tables and migrations | Core migrations and base tables exist. | users, roles, permissions, user_roles, role_permissions, audit_events created. | Implemented application_settings and an automated idempotent database seed script (app/db/seed.py) are implemented and working. | Alembic migrations and Phase 0 schema foundation validated. | PASS |  |  | Create base tables for users, roles, permissions, audit_events placeholder, application_settings and seed data. | Base migrations and seed data | Backend Engineer | SA/TL | High | Common data model | Not Started | 0% | Migrations run cleanly and seed admin/roles available | 2026-05-22 | 2026-05-27 | Phase 0 | Database
4 | 2026-05-22 | Logging, audit and health foundation | done | Implemented audit logging utility, health check, version endpoint | Structured logging , request ID, | Logging/audit/health modules reviewed successfully. | PASS |  |  | Implement structured logging, request ID, health check, version endpoint and audit logging utility placeholder. | Logging and health baseline | QA/DevOps | BE | High | API standards | Not Started | 0% | Logs contain request ID and health endpoint returns status | 2026-05-22 | 2026-05-27 | Phase 0 | Logging & Monitoring
4 | 2026-05-22 | Phase 0 integration smoke test | in progress |  |  | Initial smoke-path validation completed. | PARTIAL PASS |  | Perform full runtime integration validation with DB/frontend/auth flows. | Run frontend + backend + database together, validate API connectivity, auth flow placeholder and basic environment configuration. | Phase 0 smoke test report | QA/DevOps | BE, FE | High | Base tables, auth, UI shell | Not Started | 0% | No blocker in local/dev integrated run | 2026-05-22 | 2026-05-27 | Phase 0 | Integration
4 | 2026-05-22 | Phase 0 review and sign-off | awating |  |  | Final sign-off process still pending. | PENDING |  |  | Review Phase 0 deliverables, open issues, acceptance checklist and readiness for Phase 1 implementation. | Phase 0 sign-off checklist | Project Manager | All | High | Smoke test | Not Started | 0% | Phase 1 start approved with known issues documented | 2026-05-22 | 2026-05-27 | Phase 0 | Governance
5 | 2026-05-23 | Registry entity schema finalization | done | Finalize tables and relationships for ai_models, ai_agents, tools_registry, workflow_registry | Finalize tables and relationships for users, roles, departments and data_sources. | Registry schema foundation reviewed and partially finalized. | PASS |  |  | Finalize tables and relationships for ai_models, ai_agents, tools_registry, workflow_registry, users, roles, departments and data_sources. | Phase 1 ERD and migration design | SA/TL | BE | High | Phase 0 sign-off | Not Started | 0% | ERD reviewed and ready for migration | 2026-05-23 | 2026-05-28 | Phase 1 | Registry Data Model
5 | 2026-05-23 | Registry migrations – core entities | done | Implemented migrations for AI Model, AI Agent, Tool, Workflow | Implement migrations for Department and Data Source registries. | Jofrey: Registry migrations validated. | PASS |  |  | Implement migrations for AI Model, AI Agent, Tool, Workflow, Department and Data Source registries. | Registry migration scripts | Backend Engineer | SA/TL | High | ERD finalization | Not Started | 0% | Migrations apply and rollback successfully | 2026-05-23 | 2026-05-28 | Phase 1 | Database
5 | 2026-05-23 | Registry dashboard scaffold | done | Create Registry Dashboard route with cards/count placeholders for tools, workflows, users, | Create Registry Dashboard route with cards/count placeholders for models, agents, and departments , data sources. | Dashboard scaffold partially validated. | PARTIAL PASS |  | Add dedicated registry dashboards and registry summary widgets. | Create Registry Dashboard route with cards/count placeholders for models, agents, tools, workflows, users, departments and data sources. | Registry dashboard UI scaffold | Frontend Engineer | SA/TL | Medium | UI shell | Not Started | 0% | Dashboard route available with clean layout | 2026-05-23 | 2026-05-28 | Phase 1 | Frontend
5 | 2026-05-23 | Test strategy and data plan | in progress |  |  | Test strategy partially reviewed. | PARTIAL PASS |  | Create centralized test strategy and structured test data plan. | Prepare Phase 1 test cases, seed data scenarios, validation matrix and regression checklist. | Phase 1 test plan | QA/DevOps | PM, SA/TL | High | Phase 1 scope | Not Started | 0% | Test cases cover all registry entities | 2026-05-23 | 28-May_2026 | Phase 1 | QA
6 | 2026-05-24 | AI Model Registry APIs |  | Implemented validation, search, pagination | Implemented CRUD, duplicate prevention for AI Model Registry. | AI model registry APIs validated. | PASS |  |  | Implement CRUD, validation, search, pagination and duplicate prevention for AI Model Registry. | AI Model Registry API set | Backend Engineer | SA/TL | High | Registry migrations | Not Started | 0% | APIs pass unit/smoke tests and Swagger visible | 2026-05-24 | 2026-05-30 | Phase 1 | Backend APIs
6 | 2026-05-24 | AI Agent Registry APIs |  | Implement relationship placeholders for AI agents. | Implemented CRUD, validation, allowed execution mode, status. | PASS | PASS |  |  | Implement CRUD, validation, allowed execution mode, status and relationship placeholders for AI agents. | AI Agent Registry API set | Backend Engineer | SA/TL | High | Registry migrations | Not Started | 0% | Agent APIs create/read/update/list successfully | 2026-05-24 | 2026-05-30 | Phase 1 | Backend APIs
6 | 2026-05-24 | AI Model and Agent list pages |  | Implemented dedicated frontend pages for model and agent registry |  | Frontend registry list pages not fully available. | PASS |  | Implement dedicated frontend pages for model and agent registries. | Build list pages with table, search, filters, create/edit drawer or modal and form validations. | Model and Agent UI pages | Frontend Engineer | BE | High | Registry dashboard scaffold, APIs | Not Started | 0% | UI lists and forms connect to APIs | 2026-05-24 | 2026-05-30 | Phase 1 | Frontend
PASS
6 | 2026-05-24 | Daily build review and issue triage |  |  | No issues found | Build review process not visible in repository. | PASS |  | Introduce daily issue triage workflow and build monitoring reports. | Review progress, API/UI blockers, schema issues and reassign fixes. | Day 6 issue/action log | Project Manager | All | Medium | Daily progress | Not Started | 0% | Critical blockers identified and assigned | 2026-05-24 | 2026-05-30 | Phase 1 | Project Control
7 | 2026-05-25 | Tool and Connector Registry APIs |  |  | Registry API for Tools implemented | Registry APIs for tools/connectors not implemented. | PASS |  | Add tool and connector registry models, services, schemas, and routes. | Implement CRUD, sensitivity classification, owner, category, input/output and agent-tool mapping support. | Tool Registry APIs | Backend Engineer | SA/TL | High | Registry migrations | Not Started | 0% | Tool APIs available with mandatory sensitivity validation | 2026-05-25 | 2026-05-30 | Phase 1 | Backend APIs
7 | 2026-05-25 | Workflow Registry APIs |  | Implemented Deletion part of the CRUD. | Implemented workflow registry with CRUD operations | Workflow registry implementation missing. | PASS |  | Implement workflow registry APIs with CRUD operations and schemas. | Implement CRUD for workflows, steps, approval-required flag, department link and future policy mapping placeholder. | Workflow Registry APIs | Backend Engineer | SA/TL | High | Registry migrations | Not Started | 0% | Workflow APIs create and retrieve workflow structures | 2026-05-25 | 2026-05-30 | Phase 1 | Backend APIs
7 | 2026-05-25 | Tool Catalog and Workflow pages |  | created frontend pages for workflow and tools |  | Workflow/tool frontend screens not implemented. | PASS |  | Create frontend catalog pages and workflow management UI. | Build Tool Catalog and Workflow Registry screens with create/edit/search capabilities. | Tool and Workflow UI pages | Frontend Engineer | BE | High | Tool/Workflow APIs | Not Started | 0% | UI can create and edit tools/workflows | 2026-05-25 | 2026-05-30 | Phase 1 | Frontend
7 | 2026-05-25 | API validation testing cycle 1 |  |  |  | API validation cycle partially completed. | PASS |  | Add automated API validation and integration test coverage. | Execute API tests for model, agent, tool and workflow registries including negative scenarios. | API test results cycle 1 | QA/DevOps | BE | High | APIs complete | Not Started | 0% | High-priority API defects logged | 2026-05-25 | 2026-05-30 | Phase 1 | QA
8 | 2026-05-26 | User, Role and Department Registry APIs |  | Implemented role mapping, Deletion part of CRUD, | Finished working with implementation of user/role/department CRUD, department ownership and approval responsibility placeholders. | User/role/department APIs partially validated. | PASS |  | Separate user/role registry into dedicated modular services. | Implement user/role/department CRUD, role mapping, department ownership and approval responsibility placeholders. | User/Role/Department APIs | Backend Engineer | SA/TL | High | Base auth tables | Not Started | 0% | User-role-department relationships persist correctly | 2026-05-26 | 2026-06-02 | Phase 1 | Backend APIs
8 | 2026-05-26 | Data Source Registry APIs |  | Developed the user interface form components to capture classification, sensitivity, and owner fields, and integrated them with the backend endpoints. | Designed the database schema, wrote the Alembic migrations, and built the FastAPI REST endpoints (CRUD) with strict Pydantic validation for data sources. | Datasource APIs validated successfully. | PASS |  |  | Implement data source CRUD, classification, owner, system type, sensitivity and model/workflow link placeholders. | Data Source Registry APIs | Backend Engineer | SA/TL | High | Registry migrations | Not Started | 0% | Data sources can be registered and classified | 2026-05-26 | 2026-06-02 | Phase 1 | Backend APIs
8 | 2026-05-26 | User, Role, Department and Data Source screens |  | Constructed the UI screens, handled frontend state management, and mapped the API data to the frontend data tables and lists. | Implemented the core backend validation logic, standardized API responses, and secured the REST endpoints for Users, Roles, and Departments. | Frontend management screens incomplete. | PASS |  | Implement dedicated CRUD management screens for registry modules. | Build registry screens and forms for users, roles, departments and data sources. | User/Role/Department/Data Source UI | Frontend Engineer | BE | High | APIs available | Not Started | 0% | Screens connect to APIs with validations | 2026-05-26 | 2026-06-02 | Phase 1 | Frontend
8 | 2026-05-26 | Integration environment refresh |  | Pushed to github | Used github for sharing | Environment refresh automation not available. | PASS |  | Add docker-compose, automated migrations, and seeded environment startup. | Deploy latest backend/frontend build to dev environment or shared local stack; update environment variables and smoke test. | Integrated dev build | QA/DevOps | BE, FE | High | Core APIs and UI screens | Not Started | 0% | Shared build is accessible for testing | 2026-05-26 | 2026-06-02 | Phase 1 | DevOps
9 | 2026-05-27 | Relationship mapping APIs |  | Created the frontend API integration services to send relationship payloads and handled the UI state to map these links successfully | Designed the Relationship mapping table in the database and built the backend endpoints required to query and persist these end to end connections. | Evidence: RegistryRelationship database model in 'app/modules/registry/models.py' (lines 147-159) and corresponding endpoints POST, GET, and DELETE under '/api/registry/relationships' in 'app/modules/registry/routes.py'. | PASS |  |  | Implement link endpoints or mapping tables: model-data source, agent-tool, workflow-department, workflow-policy placeholder, user-role. | Registry relationship APIs | Backend Engineer | SA/TL | High | All registry APIs | Not Started | 0% | Relationships persist and can be queried | 2026-05-27 | 2026-06-02 | Phase 1 | Registry Relationships
9 | 2026-05-27 | Registry relationship viewer |  | Designed and built the "Related Entities" detail tabs in the UI, visually displaying the linked components fetched from the aggregation endpoint. | Developed the backend aggregation query (RelationshipGroupedResponse) to efficiently fetch and separate incoming and outgoing entity links. | Evidence: React component files 'RelationshipViewer.tsx' and 'AddRelationshipModal.tsx' along with their modular stylesheets (.module.css) under 'frontend/src/components/registry/'. | PASS |  |  | Build simple relationship viewer or detail tabs showing linked tools, agents, workflows, owners and departments. | Relationship viewer UI | Frontend Engineer | BE, SA/TL | Medium | Relationship APIs | Not Started | 0% | User can view major relationships from registry details | 2026-05-27 | 2026-06-02 | Phase 1 | Frontend
9 | 2026-05-27 | Registry audit logging |  |  | created core create_audit_event backend utility, capturing JSON diffs (before/after states), and wired to the database transaction flows | Evidence: RegistryAuditEvent database model inside 'models.py', audit trail endpoint GET '/api/registry/audit/{entity_type}/{entity_id}' in 'routes.py', and React UI component 'AuditTrailViewer.tsx' under 'components/registry/'. | PASS |  |  | Capture audit events for create/update/delete operations across all registry entities. | Registry audit logs | Backend Engineer | QA/DevOps | High | Audit utility, Registry APIs | Not Started | 0% | Audit event created for each registry mutation | 2026-05-27 | 2026-06-02 | Phase 1 | Audit
9 | 2026-05-27 | UI integration testing cycle 1 |  | Standardized all API error structures (using the StandardResponse wrapper) to ensure the UI received predictable HTTP status codes and error messages. |  | Evidence: Production compilation script execution successfully bundle all modules in 8.57s into 'dist/'. Strict typecheck 'npm run typecheck' returns 0 warnings or errors. Express SPA Helmet server ('serverClient.ts') compiles cleanly. | PASS |  |  | Test UI form validations, CRUD flows, filters, empty states, error handling and API integration. | UI test results cycle 1 | QA/DevOps | FE, BE | High | Integrated dev build | Not Started | 0% | Critical UI/API defects documented | 2026-05-27 | 2026-06-02 | Phase 1 | QA
10 | 2026-05-28 | Global registry search and filters |  | Implemented the reusable search bar component, sortable table headers, and pagination UI controls across all registry screens | Developed the standardized GlobalSearchResponse and applied unified pagination parameters (page, limit, total) across all list API endpoints. | Evidence: Global search route GET '/api/registry/search' in backend routes.py, custom hook 'useRegistryFilters.ts' in 'frontend/src/hooks/', and global search inputs on all registry page screens. | PASS |  |  | Implement consistent search, filter, sort and pagination behavior across registry entities. | Search/filter capability | Backend Engineer | FE | Medium | Registry APIs | Not Started | 0% | Search and pagination work consistently | 2026-05-28 | 2026-06-04 | Phase 1 | Search & Filtering
10 | 2026-05-28 | Dashboard metrics and counts |  | Bound the API response data to the frontend dashboard cards, ensuring the UI dynamically reflects real-time system metrics and status indicators. | Wrote the optimized SQL aggregation queries to fetch live database counts for all entities and exposed them via a dashboard API endpoint. | Evidence: Summary endpoint GET '/api/registry/summary' in backend routes.py and UI dashboard screen 'RegistryDashboardPage.tsx' under 'frontend/src/pages/'. | PASS |  |  | Connect dashboard cards to real counts and status indicators for registry entities. | Live registry dashboard | Frontend Engineer | BE | Medium | Search/filter, APIs | Not Started | 0% | Dashboard reflects database counts | 2026-05-28 | 2026-06-04 | Phase 1 | Frontend
10 | 2026-05-28 | Defect fixes and stabilization |  | Fixed all the defects from API/UI testing, improved the error messages |  | Evidence: Successful execution of database seeding, resolution of React unused imports, clean index signatures in DataTable interfaces, and elimination of typescript errors. | PASS |  |  | Fix high/medium defects from API/UI testing, improve error messages, edge cases and form behavior. | Stabilized Phase 1 build | BE + FE | QA/DevOps | High | Test cycles | Not Started | 0% | No open critical defects | 2026-05-28 | 2026-06-04 | Phase 1 | Quality
10 | 2026-05-28 | Swagger and developer notes |  |  | updated the README and made it relevant with phase 1. | Evidence: Root-level access_token / refresh_token inclusion in OAuth2PasswordRequestForm login route and comprehensive docstrings/summaries on all FastAPI path decorators. | PASS |  |  | Update Swagger, endpoint examples, environment setup and module-level README for Phase 1. | Developer documentation draft | SA/TL | BE, FE | Medium | APIs stable | Not Started | 0% | Docs cover setup and API usage | 2026-05-28 | 2026-06-04 | Phase 1 | Documentation
11 | 2026-05-29 | Full regression testing |  | All testing were completed and doesn't found any valunarability |  |  | PASS |  |  | Execute end-to-end tests across Phase 0 and Phase 1, including auth, registries, audit logs and UI flows. | Regression report | QA/DevOps | All | High | Stabilized build | Not Started | 0% | No critical or blocker defects remain | 2026-05-29 | 2026-06-04 | Stabilization | Regression
11 | 2026-05-29 | Demo data and scenario setup |  | Prepared, and few were inserted before too, realistic sample models, agents, tools, workflows, departments, users and data sources for demo. |  |  | PASS |  |  | Prepare realistic sample models, agents, tools, workflows, departments, users and data sources for demo. | Demo seed data | BE | PM, FE | Medium | Registry build | Not Started | 0% | Demo data available and meaningful | 2026-05-29 | 2026-06-04 | Stabilization | UAT Preparation
11 | 2026-05-29 | Developer handover pack |  |  | created two handover file for backend and frontend each. created user guide README file. created a file which tells about folder map, set guide, api summary. |  | PASS |  |  | Prepare folder map, setup steps, API summary, UI screen list, known issues and next-phase notes. | Handover pack | SA/TL | PM, BE, FE, QA/DevOps | High | Docs draft | Not Started | 0% | Developers can onboard using the pack | 2026-05-29 | 2026-06-04 | Stabilization | Handover
11 | 2026-05-29 | Acceptance review preparation | Few additional changes are suggested, development in progress |  |  |  | PASS |  |  | Prepare acceptance checklist, walkthrough script, completion summary and pending issue matrix. | Acceptance pack | Project Manager | QA/DevOps, SA/TL | High | Regression report | Not Started | 0% | Ready for final review | 2026-05-29 | 2026-06-04 | Stabilization | Project Control
12 | 2026-05-30 | Final demo and walkthrough | proposed demo date: 11/06/2026 |  |  |  | PASS |  |  | Demonstrate Phase 0 foundation and Phase 1 registry flows: create model, agent, tool, workflow, user/role, data source and audit log. | Final demo completed | Project Manager | All | High | Acceptance pack | Not Started | 0% | Stakeholders confirm MVP readiness | 2026-05-30 | 2026-06-10 | Closure | Demo
12 | 2026-05-30 | Acceptance and sign-off | Completed with Change log |  |  |  | PASS |  |  | Review acceptance criteria, issue log, risk register and agree completion status. | Sign-off record | Project Manager | SA/TL, QA/DevOps | High | Final demo | Not Started | 0% | Sign-off or conditional sign-off captured | 2026-05-30 | 2026-06-10 | Closure | Acceptance
12 | 2026-05-30 | Policy & Rule Engine readiness backlog | given as per phase 2 |  |  |  | PASS |  |  | Prepare Phase 2 backlog: policy tables, rule builder, evaluation API, approval matrix, governance events dependency. | Phase 2 implementation backlog | SA/TL | PM, BE, FE | Medium | Phase 1 acceptance | Not Started | 0% | Phase 2 backlog prioritized | 2026-05-30 | 2026-06-10 | Closure | Phase 2 Readiness
12 | 2026-05-30 | Package release candidate | uploaded to Github |  |  |  | PASS |  |  | Tag code, export database migration status, archive docs, create release notes and deployment instructions. | Release candidate and notes | QA/DevOps | All | High | Acceptance | Not Started | 0% | Code and documents packaged cleanly | 2026-05-30 | 2026-06-10 | Closure | Release

## Change Log
Change ID | Module | Change Description | What changed? | Who changed it? | When was it changed? | Why was it changed? | Suggestion | Status
CL-001 | Model Registry | Make Provider field mandatory with frontend and backend validation | Added 'required' validations on UI forms and strict Pydantic model checks on API routes. | Aayush |  | to ensure data integrity and prevent incomplete provider entries in the registry. |  | Completed
CL-002 | Model Registry | Replace Provider field with Provider Type, Provider Name, and Provider Details structure | Split the single text field into structured data inputs (Type, Name, Details) in both UI and DB. |  |  | To capture more granular, structured information about model providers. |  | Completed
CL-003 | Model Registry | Add additional provider governance fields (Owner, Developed By, Training Data, Hosting, Security, Usage Controls, Evaluation Details, Responsible Person) | Added fields: Owner, Developed By, Training Data, Hosting, Security, Usage Controls, Evaluation Details, Responsible Person. |  |  | To meet strict compliance and comprehensive AI governance requirements. |  | Completed
CL-004 | Database | Create registry.ai_model_providers table with provider metadata and governance attributes | Created a dedicated SQL table to store the expanded provider metadata. |  |  | To normalize the database schema and manage providers as independent, reusable entities. |  | Completed
CL-005 | Database | Update AI Model Registry to use provider_id relationship instead of provider text field | Replaced the raw text column with a foreign key linking to the new provider table. |  |  | To establish proper referential integrity between AI models and their providers. |  | Completed
CL-006 | Workflow View | Redesign Workflow lifecycle view to align with governance and operational workflow stages | Updated the workflow detail UI to visually represent exact governance pipeline stages. |  |  | To provide better visibility and tracking of a workflow's maturity and approval state. |  | Completed
CL-007 | Relationship View | Redesign Relationship View to improve mapping between workflows, agents, models, tools, and data sources | Enhanced the interactive node graph to better visualize complex asset linkages. |  |  | To make it easier for users to understand deep asset interdependencies. |  | Completed
CL-008 | Dashboard | audit metric card need to be dynamic | Wired the audit metric card to fetch live data from the backend audit endpoints. |  |  | To display accurate, real-time system metrics instead of static mock data. |  | Completed
CL-009 | Registry | add registry all button | Introduced a new "Register All" UI button and mapped it to batch processing routes. |  |  | To significantly streamline the bulk onboarding process of multiple assets. |  | Completed
CL-010 | Execution | Execution Dashboard Cumulative Metric Tiles | Added summary tiles displaying total AWAITING_APPROVAL and COMPLETED workflows. |  |  | To provide an immediate, at-a-glance summary of operational workflow bottlenecks. |  | Completed
CL-011 | Execution | Rejection/Revocation Reason Auditing: | Added a mandatory text reason modal before rejecting/revoking, storing the reason in the DB. |  |  | For strict auditing and tracking of manual intervention decisions by administrators. |  | Completed
CL-012 | Execution | Dashboard "Active Tenants" Dynamic | Connected the tenant metric tile to live authentication session logs. |  |  | To accurately reflect the true number of concurrent user sessions on the platform. |  | Completed
CL-013 | Left Pannel | Collapsible Global Sidebar Navigation: | Added a vertically centered toggle arrow to expand/collapse the left sidebar menu. |  |  | To improve UX and maximize the available screen space for main dashboard content. |  | Completed
CL-014 | All pages | Required a hint button in all the pages | Placed a Hint Bulb on each modules to help users. |  |  |  |  | Completed
CL-015 | User&Roles | when new user is created, it saves new user without dept and role as per scope of project ideallythis has to be mandetory | Made the required filed mandatory. |  |  |  |  | Completed

## MOM
Meeting Date | Project Name | Task ID | Discussion Point / Task | Owner | Status | Decision / Remarks | Action Required | Target Date
2026-06-04 | GuardianIQ | T1 | Increase size of registry form windows for all registries | Development Team | Completed | Improve usability and reduce scrolling | Implement UI changes | 2026-06-04
2026-06-04 | GuardianIQ | T2 | Perform internal testing of implemented features | Development Team | Completed | Verify features before QA review | Execute testing and document findings | 2026-06-04
2026-06-04 | GuardianIQ | T3 | Add Owner Name column to Model Registry list view | Development Team | Completed | Improve visibility of ownership details | Update UI and validate | 2026-06-04

## Resource Role Assigned
GuardianIQ Team Structure & Responsibilities
Role | Short Code | Primary Responsibility | Phase Coverage | Key Accountability | Backup / Dependency | Person Assigned
Project Manager | PM | Overall planning, governance, daily standups, risk/issues, sign-off coordination | All phases | Daily tracking, stakeholder updates, decision management | Cross-functional support as required | Jitendra Gupta
Solution Architect / Tech Lead | SA/TL | Architecture, data model, API contracts, technical reviews, integration decisions | Phase 0 & Phase 1 | Final design authority and code review | Cross-functional support as required | Jofrey
Backend Engineer | BE | FastAPI services, PostgreSQL schemas, migrations, business logic, Swagger APIs | Phase 0 & Phase 1 | Owns backend implementation and service testing | Cross-functional support as required | Aayush, Pankaj
Frontend Engineer | FE | React/Vite/Tailwind UI, screens, forms, services, integration with APIs | Phase 0 & Phase 1 | Owns user-facing registry experience | Cross-functional support as required
QA & DevOps Engineer | QA/DevOps | Environment setup, CI/CD, test plan, regression, deployment readiness, monitoring checks | Phase 0 & Phase 1 | Owns quality gates and environment readiness | Cross-functional support as required
Role Allocation Principles
Principle |  | Details
One technical decision owner |  | SA/TL owns architecture, data model, API contract and integration decisions.
Backend before UI integration |  | Backend schemas and APIs must be available before full UI integration starts.
Daily integration discipline |  | Every day ends with code merge, smoke test and issue log update.
Audit from day one |  | All registry create/update/delete actions must have audit hooks or event logging placeholders.

## Learning From Project
S. No. | Reference | Problem Statement | Solution Provided | Learning | Updated By
1 | Communication | Tasks were delayed because blockers were not communicated on time. | Shared daily updates and raised blockers early. | Early communication prevents delays and builds trust with stakeholders.
2 | Requirement Gathering | Feature was implemented incorrectly due to unclear requirements. | Conducted requirement clarification meetings before development. | Spend more time understanding the problem before writing code.
3 | Team Collaboration | Dependency on another team delayed task completion. | Coordinated with stakeholders and followed up proactively. | Getting work done often requires collaboration, not just individual effort.
4 | Time Estimation | Task estimated for 2 hours took 2 days. | Broke work into smaller subtasks and identified risks. | Software estimation is difficult; always account for unknowns.
5 | Documentation | Team members struggled to understand implementation details. | Added README, API documentation, and comments. | Good documentation saves future development time.
6 | Testing | Bug discovered after deployment. | Added unit tests and tested edge cases before release. | Code is not complete until it is tested thoroughly.
7 | Ownership | Issue remained unresolved because no one owned it. | Took responsibility and drove the resolution. | Ownership creates visibility and trust within teams.
8 | Meetings | Misalignment between developers and stakeholders. | Participated actively in discussions and clarified action items. | Meetings are for alignment and decision-making, not just status updates.
9 | Business Understanding | Feature added little customer value. | Understood user needs and business goals before implementation. | Technical solutions should solve business problems.
10 | Visibility | Contributions were not recognized. | Shared progress updates and demos regularly. | work should be communicated to create impact.
11 | Learning New Technology | Assigned a tool/framework with no prior experience. | Used documentation, tutorials, and experimentation. | Learning ability is more valuable than existing knowledge.
12 | Production Bug | Root cause was difficult to identify. | Used logs, monitoring, and systematic debugging. | Debugging is a structured investigation process.
13 | Knowledge Sharing | Team repeatedly solved the same problems. | Shared findings through documentation and demos. | Knowledge sharing increases team productivity.
14 | Professionalism | Urgent requests caused stress and confusion. | Responded calmly and communicated expectations clearly. | Professional behavior is important during pressure situations.