## Phase2 Plan
WBS | Phase | Activity | Deliverables | Issues Identified | Solution Suggested | Ayush | Pankaj | Poorvith | Owner | Support | Start Date | End Date | Status | Reason for Delay | Dependencies | Acceptance Criteria
2.1 | Phase 2 | Kickoff and review of Phase 2 specifications and visuals | Approved scope, backlog and ownership | [5 empty] | Project Manager | All | 15-Jun-2026 | 15-Jun-2026 | Completed |  | Phase 1 complete | Backlog approved
2.2 | Phase 2 | Finalize DB schema (workflow scheduling, runs, outputs, failures, events) | DDL and migration scripts |  |  | Designed Alembic migrations to create phase2_workflow_schedules, workflow_schedule_agent_assignments, approvals, and execution logs tables. |  |  | Aayush | Pankaj, PM | 15-Jun-2026 | 15-Jun-2026 | Completed |  | Phase 1 DB ready | Schema signed off
2.3 | Phase 2 | Create PostgreSQL tables, indexes, constraints and seed data | Working DB foundation |  |  | Created ORM models and repository wrappers for scheduler modules to perform robust CRUD queries. |  |  | Aayush | Pankaj | 15-Jun-2026 | 16-Jun-2026 | Completed |  | DDL finalized | Tables validated
2.4 | Phase 2 | Develop backend entities, ORM models and repositories | Repository layer |  |  | Created ORM models and repository wrappers for scheduler modules to perform robust CRUD queries. |  |  | Aayush | Pankaj | 15-Jun-2026 | 16-Jun-2026 | Completed |  | DB foundation | CRUD functional
2.5 | Phase 2 | Implement workflow registry APIs | Workflow APIs |  |  | Created registry module REST routers and logic handlers for registering workflow actions. |  |  | Aayush | Pankaj | 16-Jun-2026 | 17-Jun-2026 | Completed |  | Repositories complete | Swagger verified
2.6 | Phase 2 | Implement schedule configuration APIs | Schedule APIs |  |  | Created API endpoints for schedule management and Pydantic schemas for scheduler configuration settings. |  |  | Aayush | Pankaj | 16-Jun-2026 | 17-Jun-2026 | Completed |  | Workflow APIs | Validation complete
2.7 | Phase 2 | Implement scheduler service and workflow run engine | Scheduler engine |  |  | Programmed state transitions, next execution times via croniter, and execution triggers in workflow_scheduler/service.py. |  |  | Aayush | Pankaj | 16-Jun-2026 | 18-Jun-2026 | Completed |  | Schedule APIs | Runs triggered successfully
2.8 | Phase 2 | Implement audit events, execution logs and notifications services | Audit services |  |  |  | Designed audit logs writer services, system alerts, and notification triggers for execution tracking |  | Pankaj | Aayush | 17-Jun-2026 | 18-Jun-2026 | Completed |  | Scheduler ready | Events persisted
2.9 | Phase 2 | Implement AI Agent Boundary validation service | Boundary engine |  |  |  | Wrote agent boundary validator rules and runtime middleware checks to reject unauthorized operations. |  | Aayush | Pankaj | 17-Jun-2026 | 18-Jun-2026 | Completed |  | Registry available | Blocked actions enforced
2.10 | Phase 2 | Develop frontend route structure and navigation | Menus and routes |  |  |  |  | Set up navigation menus, sidebar paths, React router paths in AppRouter.tsx, and ProtectedRoute guards. | Poorvith | Aayush | 15-Jun-2026 | 16-Jun-2026 | Completed |  | Specifications approved | Navigation functional
2.11 | Phase 2 | Develop Workflow List and Workflow Details screens | Workflow UI |  |  |  |  | Built list grids and detailed schedule configurators under RegistryWorkflowsPage and ScheduleDetailPage. | Poorvith | Aayush | 16-Jun-2026 | 17-Jun-2026 | Completed |  | Routes ready | Responsive screens completed
2.12 | Phase 2 | Develop Create Schedule Wizard (6-step flow) | Wizard UI |  |  |  |  | Created the multi-step wizard workflow layout and configured the visual CronExpressionBuilder selector component. | Poorvith | Aayush | 16-Jun-2026 | 18-Jun-2026 | Completed |  | Workflow screens | All steps operational
2.13 | Phase 2 | Develop Schedule Lifecycle and Run History screens | Lifecycle UI |  |  |  |  | Developed run grids, detail charts, status badges, and approvals list screens under RunHistoryPage. | Poorvith | Pankaj | 17-Jun-2026 | 19-Jun-2026 | Completed |  | APIs available | Runs and statuses visible
2.14 | Phase 2 | Develop AI Agent Boundary Management screens | Boundary configuration UI |  |  |  |  | Built agent-to-model permission assignment panel matrices, rule editors, and restriction rules configs. | Poorvith | Aayush | 17-Jun-2026 | 19-Jun-2026 | Completed |  | Boundary APIs | Rules configurable
2.15 | Phase 2 | Develop dashboards and notification screens | Monitoring UI |  |  |  |  | Coded dashboard statistics, metrics, charts, and notification indicators on ExecutionDashboardPage. | Poorvith | Pankaj | 19-Jun-2026 | 20-Jun-2026 | Completed |  | Audit APIs | Dashboard functional
2.16 | Phase 2 | API integration and end-to-end frontend binding | Integrated application |  |  |  |  | Wired screens to backend endpoints via phase2Client.ts handlers and verified page states. | Poorvith | Aayush | 19-Jun-2026 | 20-Jun-2026 | Completed |  | UI and APIs complete | No broken flows
2.17 | Phase 2 | Backend unit testing and integration testing | Test reports and fixes | found some UI elements missmatch |  |  | Authored backend unit and integration test coverage verifying routes, schemas, and engine behavior. |  | Pankaj | Aayush | 19-Jun-2026 | 20-Jun-2026 | Completed | identified UI element alignments misplaced | Features completed | 80%+ pass rate
2.18 | Phase 2 | Functional QA and regression testing | QA report | [5 empty] | Pankaj | Poorvith | 20-Jun-2026 | 21-Jun-2026 | Completed |  | Integrated build | Critical defects closed
2.19 | Phase 2 | UAT walkthrough and defect triage | UAT sign-off | [5 empty] | Project Manager | All | 21-Jun-2026 | 21-Jun-2026 | Completed |  | QA complete | Business approval obtained
2.20 | Phase 2 | Documentation, deployment package and handover | Deployment guide and handover pack | [5 empty] | Project Manager | All | 21-Jun-2026 | 21-Jun-2026 | Completed |  | UAT sign-off | Phase 2 handed over

## Change Log
Date | Change ID | Module | Change Description | Scenario | What changed? | Why was it changed? | Suggestion | Status
| CL-001 | Regitry All | Add Graphical representation of relationship for better understanding |  | Graphical representation is added | initial list representation was hard to understand |  | Completed
| CL-002 | Regitry All | Add 2nd layer of approver for workflow |  | Added one more approver | in case workflow is not approved by first approver in due time, its forworded to 2nd approver |  | Completed
2026-06-25 |  |  | Verify the duplication check for workflow names.
Clarify the metadata (agent name and model name) used in the workflow and the assigned approver.
|  |  | Confirm whether the approver can approve the workflow while it is in a running or paused state. | if the approval time is missed, wil the workflow will get approved, will it be retired, will it run, will it assign to new approver
The Create and Approve fields are missing in the Workflow Scheduler History.
|  |  | When opening history from the Workflow tab, the filtering does not work correctly. Filter is not working in run history page. |  | Work code is missing in heading
A workflow can currently be created without an agent – is this mandatory or should it be enforced?
|  |  | Navigation Check |  | add back button
universal search in the header is not working in all the screen

## Learning from Project
S. No. | Reference | Problem Statement | Solution Provided | Learning | Updated By
1 | Authorization Matrix | Authorization matrix was not clearly defined before implementation. User roles, permissions, and access hierarchy were unclear. | Created a detailed authorization matrix defining roles, permissions, screen access, and CRUD operations for each user type. | Understanding the implementation and overall workflow is more important than coding directly from specifications. A clear authorization design prevents rework and implementation issues. | Pankaj, Aayush
2 | Authorization Matrix | Need to implement role-based access control (RBAC) with proper user hierarchy and screen-level permissions. | Defined user hierarchy, configured Add/Edit/View/Delete permissions, implemented access control mechanisms, and assigned screen visibility based on user roles. | Always define the hierarchy first, then map permissions (Add, Edit, View, Delete), control mechanisms, and screen accessibility for every user before development. | Pankaj, Aayush
3 | Workflow Lifecycle & State Machines | Implementation of complex scheduling and execution workflows without detailed specifications leads to gaps in status transition validation, timezone handling, and execution sequencing. | Conducted a thorough audit of the scheduler and run services against the Phase 2 Developer Spec, adding rigorous validations for cron patterns, timezone settings, and state machine transitions. | Understanding the implementation and workflow is more important before coding. Specifications act as a blueprint to avoid architectural misalignment and logic gaps. | Pankaj, Aayush
4 | RBAC & ABAC Authorization | Securing sensitive API endpoints and restricting action buttons in UI (add, edit, delete, run-now) based on roles, hierarchy, and context without a standardized access control model. | Implemented a comprehensive Authorization Decision Service combining RBAC (role-based) and ABAC (attribute-based, department, risk levels, and delegations) checks. Added screen-level button visibility controls and an authorization simulator. | Hierarchy, add, edit, and ABAC control mechanisms must map to a screen for each user type. Restricting views and actions based on user contexts prevents unauthorized overrides. | Pankaj, Aayush
5 | Database Schema and Migration | Database tables lacked constraints, proper indexes on high-query JSONB columns, and automatic timestamp updates, risking data corruption and poor performance. | Added schema migrations defining tables for schedules, assignments, runs, steps, and audit events. Configured unique keys, GIN indexes on JSONB fields, and updated_at triggers. | Database schema integrity is the foundation of AI governance. Applying constraints, GIN indexes on JSONB, and automated audit triggers ensures reliable execution tracking. | Pankaj, Aayush
6 | SQLAlchemy Models and validation | Risk of saving invalid cron schedules, mismatched execution modes, or incorrect timezone configurations due to lack of validation on input payloads. | Implemented SQLAlchemy models using Postgres-specific JSONB fields and designed Pydantic request schemas with custom validators for cron syntax, timezone verification, and confidence boundaries. | Moving validation to the schema input boundary (Pydantic field validators) catches invalid configurations before they hit the database, reducing backend complexity. | Pankaj, Aayush
7 | AI Agent Boundary Checker | AI agents could execute unauthorized tools or exceed their permitted execution modes, leading to security breaches (e.g. executing write/execute tools). | Created the BoundaryChecker service to statically and dynamically validate tool calls, block execution if requested mode exceeds agent limits, and flag schedules containing write-capable tools for human approval. | Secure AI automation requires active boundary checks at both assignment (configuration) and execution (runtime) stages. Any write-capable tools must automatically trigger human-in-the-loop approvals. | Pankaj, Aayush
8 | Run Engine and Steps Timeline | Monitoring complex multi-agent execution was difficult due to lack of visibility into intermediate states, execution times, and transient failure recovery. | Built a 6-step run engine generating 4 distinct audit steps (POLICY_CHECK, BOUNDARY_CHECK, AGENT_INVOCATION, OUTPUT_PARSING) persisted to the database. Added SLA breach tracking and retry policies. | Breaking down agent execution into discrete, persisted run steps provides deep visibility. Tracking failures by types (validation, SLA, boundary, database) allows fine-grained error recovery. | Pankaj, Aayush
9 | Scheduler Worker Concurrency | Running multiple worker instances in a horizontal scaling setup caused duplicate runs of the same due schedule. | Rewrote the due schedule query to use database-level locking FOR UPDATE SKIP LOCKED and updated next_run_at inside the locked transaction. | In a distributed deployment, atomic locking (FOR UPDATE SKIP LOCKED) is mandatory to guarantee exact-once execution and prevent duplicate triggers. | Pankaj, Aayush
10 | Centralized Governance Event Logs | Lack of a centralized, tampering-resistant audit log for actions like schedule creation, activation, run failure, and boundary checks. | Developed the GovernanceEventService to publish 19 distinct event codes to a unified audit_events table and attached a database trigger that rejects updates or deletes (immutability). | Compliance logs must be immutable. Implementing database-level triggers that block updates/deletes ensures audit trail integrity, satisfying stringent security regulations. | Pankaj, Aayush
11 | Create Wizard & Dashboard UX | Configuring schedules, agent assignments, and boundaries is complex for end-users, leading to setup mistakes. | Designed a 6-step Create Schedule Wizard including a CronExpressionBuilder, dynamic risk-warning banners, and permission-based action visibility on the dashboard. | Intricate security policies (like tool blocks and risk levels) must be guided by clean wizard-based UI designs, alert banners, and interactive builders to eliminate user configuration errors. | Poorvith
12 | Run Detail & Approval Queue UI | Approvers and auditors lacked intuitive tools to review pending changes, see run steps timeline, or inspect evidence. | Built the Approval Queue table, details panel (highlighting write tools and risk warnings), and Run Detail Page showing an interactive steps timeline, findings, and JSON evidence viewer. | Visualizing the execution timeline (with colored status states) and highlighting high-risk actions (in amber/red) makes human review efficient and reduces sign-off delays. | Poorvith
13 | Test Suite Integrity | Hidden setup bugs in the testing suite (like the tool allowlist default override) caused false positives, indicating security checks were working when they were bypassed. | Patched tool allowlist logic in test fixtures to handle empty lists explicitly and expanded authorization negative tests to cover 22 scenarios. | Test suites must be audited as closely as production code. Default overrides in test fixtures can lead to silent test coverage gaps, especially for security assertions. | Poorvith

## MoM
Meeting Date | Project Name | Task ID | Discussion Point / Task | Owner | Status | Decision / Remarks | Action Required | Target Date
2026-06-16 | GuardianIQ | T1-4 | 1. Push the phase 0 and phase 1 code to officical repo. 2. Create the MoM sheet and update it. 3. Fill the learning sheet of Previous Phases. 4. Actual date to be filled in sheet of previous Phases. | Aayush, Pankaj, Poorvith | Done |  |  | 2026-06-16
2026-06-17 | GuardianIQ | T1-3 | 1. Specification, workflow (understanding it and finding missing for clarity) 2. phase 1 installation - bat 3. inserting more field to the phase 2 sheet like there was in phase 1. | Aayush, Pankaj | Done |  |  | 2026-06-17
2026-06-18 | GuardianIQ | T1-2 | 1. Add graphical feature for relationships and 2nd layer of approver for workflow 2. Update change log sheet with above features | Aayush, Pankaj | Done |  |  | 2026-06-18
2026-06-23 | GuardianIQ | T1-2 | 1. Perform internal testing of all features 2. Generate sample data for new modules | Aayush, Pankaj, Poorvith | Done | Issues were identified in Agent Assignment | rework the logic of schedule status once changes were made | 2026-06-23
2026-06-24 | GuardianIQ | T1 | 1. Perform Internal testing of all the features. | Poorvith | Done |  |  | 2026-06-24
2026-06-25 | GuardianIQ | T1-8 | 1. Verify the duplication check for workflow names. 2. Clarify the tools used in the workflow and the assigned approver. 3. Confirm whether the approver can approve the workflow while it is in a running or paused state. 4. The Create and Approve fields are missing in the Workflow Scheduler History. 5. When opening history from the Workflow tab, the filtering does not work correctly. 6. A workflow can currently be created without an agent – is this mandatory or should it be enforced? 7. Navigation Check 8. Filter is not working in run history page. | Aayush, Pankaj |  |  |  | 2026-06-25