GuardianIQ Phase 3 - Scope Alignment & Audit Report

Assessment of Phase 3 relationship implementation against EA Guide (Vol 1) and UX Foundation (Vol 2A) Specifications

# 1. Executive Summary

This report provides a formal scope alignment assessment of the Phase 3 Relationship Architecture deliverables for the GuardianIQ platform. It evaluates the 25 tasks documented in the task execution checklist against the baseline requirements established in two canonical guidebooks: GuardianIQ Volume 1 - Relationship Architecture & Enterprise Implementation Guide (EA Guide) and Volume 2A - UX Foundation & Information Architecture (UX Foundation).

Key Assessment Highlights:

Scope Alignment: 100% of the Audited Tasks are IN-SCOPE. Every task listed directly corresponds to a database model, REST API endpoint, security control, UI panel, or project delivery milestone defined in the Architecture and UX reference manuals. No out-of-scope work or feature bloat was introduced.

Implementation Progress: Out of the 25 planned activities, 11 tasks are Complete (including DDL migrations, ORM compilation, repositories layer, basic CRUD services, and the timeline UI), 9 tasks are Partially Implemented (requiring additional coverage for graph visualizers, wizards, permission scopes, and caching), and 5 tasks are Missed (lacking composite traversal indexes, seed script data, OpenAPI spec documents, mapping matrices, and QA automation suites).

Critical Security and Traversal Gaps: While the core database mappings and CRUD operations are fully functional, major gaps exist in the resolver layer (missing policy and evidence graph bindings), the authorization bridge (missing node-level masking and validation on delete/suspend paths), and the visualizer layout (lack of depth controls and risk indicators).

# 2. Scope Alignment Matrix

The following matrix maps each task to its reference section in the guidebooks, evaluating scope alignment, implementation status, and remaining gap justifications:

| Task & Activity | WBS Reference | Ref Section | Scope Status | Impl. Status | Gaps / Notes |
| --- | --- | --- | --- | --- | --- |
| Task 1: Write DDL migrations | [2.1] | EA Guide Spec p.17-18 | In-Scope | Complete | Migrations created tables for relationships, responsibilities, snapshots, rules, bindings, and evidence links successfully. |
| Task 2: Create indexes and constraints | [2.2] | EA Guide Sec J p.17 | In-Scope | Missed | Missing composite indexes for source, target, and lifecycle lookups; only single-column indexes were created. |
| Task 3: Create seed/reference data | [2.3] | EA Guide Sec D & H | In-Scope | Missed | No database seed script exists. Enums are defined in code only. |
| Task 4: Implement ORM models | [2.4] | EA Guide Sec F & G | In-Scope | Complete | SQLAlchemy models and Pydantic schemas created and compile cleanly. |
| Task 5: Implement repositories | [2.5] | EA Guide Sec I & J | In-Scope | Complete | Relationship and Responsibility repository layers are implemented and cover query constraints. |
| Task 6: Prepare shell screens | [2.6] | UX Found. Sec 7 | In-Scope | Complete | Shell views for explorer, panel, graph visualizer, and wizard created with placeholder integrations. |
| Task 7: Relationship service CRUD | [3.1] | EA Guide Sec I | In-Scope | Complete | CRUD service manages creations, updates, revocations, and suspensions safely. |
| Task 8: Responsibility service | [3.2] | EA Guide Sec B & I | In-Scope | Complete | Resolves active primary owner, handles reviewer/approver/auditor assignments. |
| Task 9: Validation engine MVP | [3.3] | EA Guide Sec K | In-Scope | Complete | Validates source/target existence, tenant matching, dates, and duplicate links. |
| Task 10: Audit event integration | [3.4] | EA Guide Sec B & M | In-Scope | Complete | Publishes CREATE/UPDATE/REVOKE/SUSPEND/VALIDATION_FAILED events to core DB. |
| Task 11: Explorer list/table | [3.5] | UX Found. Sec 9 & 10 | In-Scope | Partial | Table renders relationships but lacks filter selectors, search input, actions column, and scope display. |
| Task 12: Create Wizard | [3.6] | UX Found. Sec 7 & 10 | In-Scope | Partial | Wizard is a single-step modal. Lacks scope, responsibility, dates, and metadata forms. |
| Task 13: Graph/resolver APIs | [4.1] | EA Guide Sec J & O | In-Scope | Partial | Resolves graph traversal, owners, and timeline, but missing policy and evidence resolution. |
| Task 14: Authorization bridge | [4.2] | EA Guide Sec L | In-Scope | Partial | ABAC write checks present on create/update, but missing on delete/suspend and graph node queries. |
| Task 15: OpenAPI contract draft | [4.3] | EA Guide Sec O | In-Scope | Missed | No dedicated spec file exists. Only auto-generated FastAPI docs are available. |
| Task 16: Object relationship panel | [4.4] | UX Found. Sec 5 & 10 | In-Scope | Partial | Panel works and is embedded in Agent view, but missing from Model, Workflow, and Tool details. |
| Task 17: Graph View MVP | [4.5] | UX Found. Sec 10 & 7 | In-Scope | Partial | React Flow visualizes links, but lacks depth control slider, status filters, and risk indicators. |
| Task 18: Create mapping matrix | [5.1] | Plan Requirement | In-Scope | Missed | No mapping document connecting screens to API, service, and table exists in workspace. |
| Task 19: Relationship timeline UI | [5.2] | UX Found. Sec 7 & 10 | In-Scope | Complete | Renders timeline with state changes, before/after JSON, and actor details on detail modals. |
| Task 20: Performance & cache baseline | [5.3] | EA Guide Sec J | In-Scope | Partial | Enforces graph depth query limits, but lacks basic memory caching and update invalidations. |
| Task 21: Prepare QA test cases | [5.4] | Plan Requirement | In-Scope | Missed | No QA playbook mapping scenario requirements to executable tests exists. |
| Task 22: E2E relationship flow | [6.1] | Plan Requirement | In-Scope | Complete | Integrated UI-to-DB creation flow works. Re-fetches parent data correctly on success. |
| Task 23: Execute UI functional tests | [6.4] | Plan Requirement | In-Scope | Missed | No automated Cypress/Playwright scripts exist to test frontend boundaries. |
| Task 24: Developer handover pack | [6.5] | Plan Requirement | In-Scope | Missed | No developer handover documentation file has been written. |
| Task 25: Finalize acceptance checklist | [7.3] | Plan Requirement | In-Scope | Complete | Checklist completed, signed, and saved in implementation check file. |

# 3. Assessment of Key Gaps against Scope

## 3.1 Graph Traversal & Context (Task 13 Gap)

The Graph traversal service represents the relationship resolution backbone. Under the Phase 3 scope, this service must resolve policy bindings and evidence links connected to governance entities. The current implementation only queries the generic_relationships table, completely ignoring the policy_bindings and evidence_links tables. Consequently, policies and evidence connections are absent from the resolved graph, representing a significant architectural gap.

## 3.2 Node Filtering & Authorization (Task 14 Gap)

According to the EA Guide (Section L), the graph traversal API must enforce data confidentiality by hiding or redacting unauthorized objects based on tenant, role clearance, sensitivity levels, and department scopes. Currently, the graph API performs no node-level authorization or attribute masking, allowing users to view the entire traversed dependency graph regardless of their security clearances.

## 3.3 Performance Caching (Task 20 Gap)

Volume 1 (Section J) mandates caching of stable governance context queries and graph traversal snapshots to prevent redundant database lookups. The current implementation enforces depth query limits, but lacks an operational cache manager or invalidation routines on database mutations.

# 4. Remediation & Action Plan

To align the Phase 3 implementation with the required specifications, the following actions must be executed:

1. Database Optimizations:

Create a SQL/Alembic migration to apply composite indexes on generic_relationships (source/target query matching) and object_responsibilities columns.

Write a seed script in Python to populate sample active relationships and owner mappings.

2. API & Resolver Upgrades:

Update the graph traversal service to query policy_bindings and evidence_links and integrate them into the returned node-edge list.

Apply node-level filters inside the Graph API to replace unauthorized node details with `"[REDACTED]"` placeholder tags.

Secure write routes (revoke, suspend, approve, activate) using the ABAC access evaluator.

3. Performance Caching:

Implement an in-memory cache helper within the backend service layer to cache graph outputs, invalidating it upon write requests.

| Prepared By: ________________________ GuardianIQ Audit Lead | Approved By: ________________________ Project Manager / Team Lead |
| --- | --- |
| Date: July 16, 2026 | Status: Signed Off |