## Dashboard
GuardianIQ Phase 4 - Governance Event Architecture Implementation Plan
Plan Window | 15-Jul-2026 to 21-Jul-2026 | Phase | Phase 4 / Step 4 | Scope | Governance Event Architecture, Event Store, Event APIs, Audit Timeline, UI views, QA | Primary Source | Step 4 Foundation
KPI | Value / Formula | Target | Owner | Status | Notes
Total Activities | 42 | 45+ | PM | Tracked | Covers DB, backend, frontend, integration, QA and handover
Critical Activities | 0 | All assigned | PM | Tracked | Critical path must complete by Day 6
Completed Activities | 0 | 100% | All | Open | Update daily
Blocked Activities | 0 | 0 | PM | Open | Daily escalation
Key Deliverables | 9 | 8+ | PM | Tracked | Deliverables are sign-off gates
DB / Event Store Ready | governance_events + outbox + processing logs | Day 3 | Aayush | Planned | Foundation for all other work
Event Publisher Ready | Service + envelope + schema validation | Day 4 | Pankaj | Planned | Used by all modules
UI Timeline Ready | Event Explorer + Audit Timeline | Day 6 | Poorvith | Planned | Visible governance proof
Final Handover | Scripts + API docs + UI routes + QA evidence | Day 7 | PM | Planned | Ready for continuation

## Detailed Plan
WBS | Workstream | Activity | Detailed Task Description | Deliverable | Owner | Support | Start Date | End Date | Priority | Status | Dependencies | Acceptance Criteria | Notes
4.1.1 | Project Management | Phase 4 kickoff and scope lock | Review Step 4 foundation and lock Phase 4 MVP scope: event store, outbox, publisher service, event APIs, audit timeline, event explorer, QA. | Signed kickoff notes and sprint scope | Project Manager | All | 15-Jul-2026 | 15-Jul-2026 | Critical | Not Started | Step 4 foundation available | All owners understand event-first architecture and sprint outputs
4.1.2 | Project Management | Create sprint tracker and daily cadence | Set daily stand-up, defect triage, handover checkpoints and owner-specific outputs. | Sprint tracker and cadence | Project Manager | All | 15-Jul-2026 | 15-Jul-2026 | High | Not Started | Kickoff | Daily checkpoints scheduled and tracker shared
4.1.3 | Architecture | Confirm event taxonomy MVP | Select event categories and event types for first implementation: registry, relationship, workflow run, approval, agent action, policy, risk, audit. | Approved MVP event catalogue | Aayush | Pankaj, PM | 15-Jul-2026 | 15-Jul-2026 | Critical | Not Started | Step 4 event taxonomy | Event types finalized and mapped to source services
4.1.4 | Architecture | Finalize canonical event envelope | Freeze required fields: event_id, tenant_id, event_type, event_version, actor_json, subject_json, payload_json, correlation_id, causation_id, classification, retention_class. | Canonical event envelope spec | Pankaj | Aayush | 15-Jul-2026 | 15-Jul-2026 | Critical | Not Started | Event taxonomy | Envelope fields approved by backend/frontend/QA
4.1.5 | Database | Review Phase 0-3 data dependencies | Review existing identity, registry, workflow, relationship and audit schemas to avoid duplication and align event subject references. | Dependency assessment | Aayush | Pankaj | 15-Jul-2026 | 15-Jul-2026 | Critical | Not Started | DB access | Current tables and event touchpoints documented
4.1.6 | Frontend | Confirm UI scope for Phase 4 | Confirm screens: Event Explorer, Audit Timeline, Event Detail Drawer, Dead Letter Queue view, Audit Export request panel and dashboard widgets. | UI scope checklist | Poorvith | PM, Aayush | 15-Jul-2026 | 15-Jul-2026 | High | Not Started | Volume 2A UX foundation | Screens agreed and routes identified
4.2.1 | Database | Design event physical model | Design tables: governance_events, event_outbox, event_processing_log, event_dead_letter, event_schema_registry, event_retention_rules, event_export_log, audit_timeline_views/read model. | Physical event model | Aayush | Pankaj | 16-Jul-2026 | 16-Jul-2026 | Critical | Not Started | Dependency assessment | Tables, columns, keys, JSONB fields and indexes defined
4.2.2 | Database | Create migration scripts | Write SQL migrations for event store, outbox, processing log, dead letter, schema registry and retention rules. | DB migration scripts | Aayush | Pankaj | 16-Jul-2026 | 17-Jul-2026 | Critical | Not Started | Physical event model | Scripts run cleanly in dev DB
4.2.3 | Database | Create event indexes and constraints | Add indexes for tenant_id, event_type, occurred_at, correlation_id, subject_json, actor_json and payload_json where required. | Index and constraint script | Aayush | Pankaj | 16-Jul-2026 | 17-Jul-2026 | Critical | Not Started | DB migrations | Event query paths are supported
4.2.4 | Database | Seed event reference data | Seed event categories, event types, schema versions, retention classes, classification levels and routing topics. | Reference data seed script | Aayush | Pankaj | 16-Jul-2026 | 17-Jul-2026 | High | Not Started | DB migrations | Reference data visible to APIs/UI
4.2.5 | Backend | Create event module structure | Create backend module: events/models.py, schemas.py, repository.py, service.py, validators.py, router.py, dispatcher.py, event_types.py. | Backend event module shell | Pankaj | Aayush | 16-Jul-2026 | 16-Jul-2026 | Critical | Not Started | Event envelope spec | Module builds and imports correctly
4.2.6 | Frontend | Create UI route shells | Create route shells for Event Explorer, Audit Timeline, Event Detail, Dead Letter Queue and Audit Export. | Frontend route shells | Poorvith | Aayush | 16-Jul-2026 | 17-Jul-2026 | High | Not Started | UI scope checklist | Routes load with placeholder states
4.3.1 | Backend | Implement GovernanceEvent schemas | Implement Pydantic schemas for event create, event response, event search filters, timeline response, outbox and dead-letter records. | Event schemas | Pankaj | Aayush | 17-Jul-2026 | 17-Jul-2026 | Critical | Not Started | Event module shell | Schemas validate canonical envelope
4.3.2 | Backend | Implement EventRepository | Implement append-only insert, search by type/date/actor/subject/correlation, single event lookup, and processing status lookup. | EventRepository | Pankaj | Aayush | 17-Jul-2026 | 18-Jul-2026 | Critical | Not Started | DB migrations | Repository unit tests pass
4.3.3 | Backend | Implement EventPublisherService | Implement event creation, envelope enrichment, actor context, correlation_id handling, schema validation, event hashing and outbox enqueue. | EventPublisherService | Pankaj | Aayush | 17-Jul-2026 | 18-Jul-2026 | Critical | Not Started | Event schemas and repository | Events are persisted and outbox record created
4.3.4 | Backend | Implement event validation rules | Validate required fields, event_type, event_version, tenant_id, actor, subject, classification, retention_class and payload size/sensitivity rules. | Event validation service | Pankaj | Aayush | 17-Jul-2026 | 18-Jul-2026 | Critical | Not Started | EventPublisherService | Invalid events blocked with clear error
4.3.5 | Backend | Implement event APIs MVP | Implement POST /api/events, GET /api/events, GET /api/events/{id}, GET /api/events/subject/{type}/{id}, GET /api/events/correlation/{id}. | Event API MVP | Pankaj | Aayush | 17-Jul-2026 | 18-Jul-2026 | Critical | Not Started | Repository and publisher | APIs work in Swagger/Postman
4.3.6 | Frontend | Build Event Explorer table | Create searchable/filterable grid with event type, category, actor, subject, risk, policy, occurred_at, correlation_id, classification and status. | Event Explorer UI | Poorvith | Aayush | 17-Jul-2026 | 19-Jul-2026 | High | Not Started | Route shells and API contract | Grid binds to API and handles filters
4.4.1 | Backend | Implement outbox dispatcher | Create background dispatcher for event_outbox with status, retry_count, next_retry_at, error logging and dead-letter transition. | Outbox dispatcher | Pankaj | Aayush | 18-Jul-2026 | 19-Jul-2026 | Critical | Not Started | EventPublisherService | Outbox processing works with retries
4.4.2 | Backend | Implement processing log and dead letter APIs | Implement event processing log write/read and dead-letter list/detail/retry APIs. | Processing and DLQ APIs | Pankaj | Aayush | 18-Jul-2026 | 19-Jul-2026 | High | Not Started | Outbox dispatcher | Failed events visible and retryable
4.4.3 | Backend | Implement audit timeline service | Create timeline builder using event correlation, subject lookup, event ordering and display-friendly transformation. | AuditTimelineService | Pankaj | Aayush | 18-Jul-2026 | 19-Jul-2026 | Critical | Not Started | Event APIs | Object and correlation timelines are reconstructable
4.4.4 | Backend | Integrate event publisher with existing modules | Add event emission hooks for model registry, agent registry, relationship changes, workflow schedule/run, approval and agent boundary events where available. | Producer integrations | Aayush | Pankaj | 18-Jul-2026 | 20-Jul-2026 | Critical | Not Started | EventPublisherService | At least 5 key flows emit events
4.4.5 | Frontend | Build Event Detail Drawer | Create drawer with envelope metadata, actor, subject, risk context, policy context, payload JSON, integrity details and related timeline link. | Event Detail Drawer | Poorvith | Pankaj | 18-Jul-2026 | 19-Jul-2026 | High | Not Started | Event Explorer UI | Drawer shows full event detail and formatted JSON
4.4.6 | Frontend | Build Audit Timeline UI | Create timeline view for subject and correlation flows showing ordered events, actor, decision, status, evidence/action links and duration. | Audit Timeline UI | Poorvith | Aayush | 18-Jul-2026 | 20-Jul-2026 | Critical | Not Started | Timeline API | Timeline reconstructs event chain
4.5.1 | Backend | Implement audit export API | Create audit export request API with scope_json, event filters, export log, hash metadata and placeholder file reference. | Audit export API | Aayush | Pankaj | 19-Jul-2026 | 20-Jul-2026 | High | Not Started | Timeline service | Export request logged and traceable
4.5.2 | Backend | Implement retention and classification controls | Add retention_class enforcement metadata and classification-based event visibility filters. | Retention/classification controls | Pankaj | Aayush | 19-Jul-2026 | 20-Jul-2026 | High | Not Started | Reference data | Sensitive event access is filtered by permission
4.5.3 | Backend | Implement event metrics endpoints | Create dashboard endpoints for event counts by type/category, policy violations, SLA breaches, blocked agent actions, outbox lag and dead-letter count. | Event metrics APIs | Pankaj | Aayush | 19-Jul-2026 | 20-Jul-2026 | Medium | Not Started | Event repository | Dashboard can consume metrics
4.5.4 | Frontend | Build Dead Letter Queue screen | Create screen for failed event processing with error details, retry action, filters and status badges. | DLQ UI | Poorvith | Pankaj | 19-Jul-2026 | 20-Jul-2026 | Medium | Not Started | DLQ APIs | Failed events visible and retry action available
4.5.5 | Frontend | Build Audit Export panel | Create panel/form for audit package export by subject, correlation_id, date range, event type, classification and reason. | Audit Export UI | Poorvith | Aayush | 19-Jul-2026 | 20-Jul-2026 | Medium | Not Started | Audit export API | Export requests can be submitted
4.5.6 | Frontend | Build event dashboard widgets | Create widgets for event volume, high-risk events, policy violations, blocked agent actions, outbox lag and DLQ count. | Dashboard widgets | Poorvith | Aayush | 19-Jul-2026 | 20-Jul-2026 | Medium | Not Started | Metrics API | Widgets render current metrics
4.5.7 | Documentation | Create API and event catalogue document | Document event types, payload examples, APIs, request/response, errors, audit events and integration notes. | Event API catalogue | Aayush | Pankaj | 19-Jul-2026 | 20-Jul-2026 | High | Not Started | APIs complete | Frontend and QA can test independently
4.6.1 | Integration | E2E event publish flow | Test UI/API action → event publisher → governance_events → outbox → processing log → Event Explorer. | Integrated publish flow | Aayush | Pankaj, Poorvith | 20-Jul-2026 | 20-Jul-2026 | Critical | Not Started | APIs and UI ready | Complete publish flow passes
4.6.2 | Integration | E2E audit timeline flow | Test recommendation/workflow/agent event chain → correlation timeline → audit timeline UI → event detail drawer. | Integrated timeline flow | Poorvith | Aayush, Pankaj | 20-Jul-2026 | 20-Jul-2026 | Critical | Not Started | Timeline service/UI | Timeline reconstructs full chain
4.6.3 | Integration | E2E dead-letter/retry flow | Force consumer failure → outbox retry → dead-letter → UI review → retry. | Integrated DLQ flow | Pankaj | Poorvith, Aayush | 20-Jul-2026 | 20-Jul-2026 | High | Not Started | Dispatcher and DLQ UI | Failure is visible and recoverable
4.6.4 | QA | Execute DB/API test pack | Run tests for event schema, append-only behavior, search filters, correlation lookup, dead-letter records, retention/classification. | DB/API QA results | Pankaj | Aayush | 20-Jul-2026 | 20-Jul-2026 | Critical | Not Started | QA scenarios prepared | Critical backend tests pass
4.6.5 | QA | Execute UI functional tests | Test Event Explorer, Detail Drawer, Audit Timeline, DLQ, Audit Export, dashboard widgets, loading/empty/error states. | UI QA results | Pankaj | Poorvith | 20-Jul-2026 | 20-Jul-2026 | High | Not Started | UI integrated | Critical UI tests pass
4.6.6 | Documentation | Prepare handover pack draft | Prepare DB scripts, API catalogue, event catalogue, UI route list, test evidence and open issue log. | Handover pack draft | Project Manager | All | 20-Jul-2026 | 20-Jul-2026 | High | Not Started | Integration testing | Draft ready for final review
4.7.1 | QA | Regression and defect closure | Fix and retest critical/high defects across DB, backend APIs, frontend, integration and security/access checks. | Defect closure report | Pankaj | Aayush, Poorvith | 21-Jul-2026 | 21-Jul-2026 | Critical | Not Started | QA results | No open critical defects
4.7.2 | Security | Verify event immutability and access control | Verify normal application paths cannot update/delete events and event visibility respects tenant/RBAC/ABAC/classification. | Security verification results | Pankaj | Aayush | 21-Jul-2026 | 21-Jul-2026 | Critical | Not Started | Event APIs | Append-only and scoped access confirmed
4.7.3 | Project Management | Final UAT walkthrough | Walk through event architecture, event store, publisher, UI screens, timeline, DLQ, export and QA evidence. | UAT walkthrough notes | Project Manager | All | 21-Jul-2026 | 21-Jul-2026 | Critical | Not Started | Regression complete | Phase 4 accepted by stakeholders
4.7.4 | Documentation | Finalize handover package | Finalize implementation notes, scripts, API/event catalogue, route list, QA evidence, known issues and next backlog. | Final handover package | Project Manager | All | 21-Jul-2026 | 21-Jul-2026 | Critical | Not Started | UAT walkthrough | Developers can continue without open dependency
4.7.5 | Delivery | Create release candidate and next backlog | Package code branch, migrations, docs and create next backlog for evidence lineage, advanced replay, archival and analytics. | Release candidate and backlog | Aayush | PM, Pankaj, Poorvith | 21-Jul-2026 | 21-Jul-2026 | High | Not Started | Final handover | Release candidate ready and next sprint prioritized

## Daily Sprint
Day | Date | Primary Focus | Key Activities | Owners | Expected End-of-Day Output | PM Checkpoint
Day 1 | 15-Jul-2026 | Scope and event architecture lock | Kickoff, event taxonomy MVP, canonical envelope, DB dependency review, UI scope lock | PM, Aayush, Pankaj, Poorvith | Event architecture and sprint scope finalized | Confirm no open questions on event envelope
Day 2 | 16-Jul-2026 | Event store foundation | Physical model, migrations, indexes, seed data, backend module shell, frontend route shells | Aayush, Pankaj, Poorvith | DB and route foundation ready | Confirm scripts run and route shells load
Day 3 | 17-Jul-2026 | Publisher and core APIs | Schemas, repository, publisher service, validation, event APIs, Event Explorer start | Pankaj, Aayush, Poorvith | Events can be published and searched | Review APIs with frontend and QA
Day 4 | 18-Jul-2026 | Dispatcher and timeline | Outbox dispatcher, processing logs, DLQ APIs, audit timeline service, event detail and timeline UI | Pankaj, Poorvith, Aayush | Timeline and dispatcher capabilities usable | Confirm correlation timeline works
Day 5 | 19-Jul-2026 | Controls and UI completion | Audit export, retention/classification, metrics API, DLQ UI, export panel, dashboard widgets, event catalogue | Aayush, Pankaj, Poorvith | Feature-complete MVP | Review open defects before integration day
Day 6 | 20-Jul-2026 | Integration and QA | E2E publish flow, timeline flow, DLQ flow, DB/API QA, UI QA, handover draft | All | Integrated working Phase 4 build | Escalate critical/high defects only
Day 7 | 21-Jul-2026 | Stabilization and handover | Regression, immutability/access verification, UAT walkthrough, final handover, release candidate | All | Phase 4 accepted and handed over | Final sign-off and next backlog

## Deliverables
ID | Deliverable | Description | Owner | Support | Due Date | Acceptance Criteria | Status
D4-01 | Phase 4 Sprint Scope | Approved scope, sprint tracker and daily cadence for event architecture implementation. | Project Manager | All | 15-Jul-2026 | Scope signed off; team aligned | Not Started
D4-02 | Event Taxonomy and Envelope | MVP event catalogue and canonical governance event envelope. | Pankaj | Aayush | 15-Jul-2026 | Required fields and event types approved | Not Started
D4-03 | Event Store Physical Schema | governance_events, outbox, processing log, dead-letter, schema registry, retention and export log tables. | Aayush | Pankaj | 17-Jul-2026 | Migration scripts run cleanly | Not Started
D4-04 | Event Publisher and APIs | Publisher service, validation, event repository and event query APIs. | Pankaj | Aayush | 18-Jul-2026 | Events publish, validate and query successfully | Not Started
D4-05 | Outbox and Timeline Services | Dispatcher, processing log, DLQ handling and audit timeline service. | Pankaj | Aayush | 19-Jul-2026 | Timeline reconstructs correlated lifecycle | Not Started
D4-06 | Frontend Event UI | Event Explorer, Event Detail Drawer, Audit Timeline, DLQ View, Export Panel and dashboard widgets. | Poorvith | Aayush, Pankaj | 20-Jul-2026 | Screens integrated with APIs | Not Started
D4-07 | API and Event Catalogue | Documented APIs, event types, payload examples, errors and integration notes. | Aayush | Pankaj | 20-Jul-2026 | Developer-ready catalogue complete | Not Started
D4-08 | QA Evidence Pack | DB/API/UI/security/integration test results and defect closure report. | Pankaj | All | 21-Jul-2026 | No open critical defects | Not Started
D4-09 | Final Handover and Release Candidate | Scripts, code branch, UI route list, API docs, event catalogue, QA results and next backlog. | Project Manager | All | 21-Jul-2026 | Phase 4 handover complete | Not Started

## RACI
Deliverable / Activity | Project Manager | Aayush | Pankaj | Poorvith | Notes
Sprint governance and scope control | A/R | C | C | C | PM owns delivery cadence and sign-off
Event taxonomy and canonical envelope | C | C | A/R | I | Pankaj owns event service correctness
PostgreSQL event store schema | I | A/R | C | I | Aayush owns physical data model and migrations
Event repository and publisher service | I | C | A/R | I | Pankaj owns backend service implementation
Outbox dispatcher and DLQ | I | C | A/R | I | Reliability layer for event processing
Existing module producer integrations | I | A/R | R | I | Aayush coordinates integration with existing backend
Event Explorer UI | I | C | C | A/R | Poorvith owns UI
Audit Timeline UI | I | C | C | A/R | Poorvith owns UI, Pankaj validates event data
Dead Letter Queue UI | I | C | C | A/R | Poorvith builds, Pankaj validates backend
API and Event Catalogue | I | A/R | C | C | Used by frontend and QA
QA test execution and evidence | A | C | R | C | Pankaj owns QA completion
UAT walkthrough and final handover | A/R | C | C | C | PM owns closure

## Dependencies
ID | Dependency | Required By | Owner | Due Date | Risk if Missing | Mitigation | Status
DEP-01 | Existing Phase 0-3 DB schema access | DB design and integrations | Aayush | 15-Jul-2026 | Duplicate/misaligned tables | Review DB first before DDL | Open
DEP-02 | Actor/context and auth mechanism | Event publisher actor enrichment | Pankaj | 17-Jul-2026 | Events miss accountability | Use current auth context wrapper | Open
DEP-03 | Existing audit/notification patterns | Audit timeline and downstream consumers | Pankaj | 18-Jul-2026 | Duplicate audit logic | Integrate where available; otherwise stub cleanly | Open
DEP-04 | Frontend API contract | UI implementation | Aayush | 17-Jul-2026 | Poorvith blocked | Mock contract by Day 3 | Open
DEP-05 | Event reference data | APIs and UI filters | Aayush | 17-Jul-2026 | Inconsistent event names | Seed event master tables | Open
DEP-06 | Test environment DB | QA and integration | Project Manager | 16-Jul-2026 | Testing delayed | Confirm dev/test environment on Day 1 | Open
DEP-07 | Phase 4 implementation spec | Team reference | Project Manager | 15-Jul-2026 | Scope confusion | Use as sprint base | Open

## Risks
Risk ID | Risk / Issue | Impact | Probability | Severity | Owner | Mitigation | Early Warning | Status
R4-01 | Event architecture becomes too broad for one week | Timeline miss | Medium | High | Project Manager | Limit MVP to event store, publisher, query, timeline, DLQ and key producer hooks | Requests for advanced analytics/replay | Open
R4-02 | Outbox dispatcher reliability issues | Event loss or duplicate processing | Medium | Critical | Pankaj | Implement idempotent processing and retry status clearly | Repeated failed dispatches | Open
R4-03 | Event payload contains sensitive data | Privacy/security risk | Low | Critical | Pankaj | Use references/masking; apply classification review | Raw data appears in payload | Open
R4-04 | Frontend blocked by backend APIs | UI delays | Medium | High | Aayush | Provide API contract and mock data by Day 3 | UI routes remain placeholders | Open
R4-05 | Timeline reconstruction incomplete | Audit value reduced | Medium | High | Pankaj | Enforce correlation_id and subject references in publisher | Events missing correlation_id | Open
R4-06 | DB query performance poor | Slow explorer/timeline | Medium | Medium | Aayush | Create indexes for event_type/time/correlation/subject JSONB | Event Explorer slow | Open
R4-07 | Audit immutability not enforced | Governance failure | Low | Critical | Pankaj | Block update/delete APIs; use append-only permission model | Events editable in normal path | Open
R4-08 | Too many producer integrations attempted | Core not stabilized | Medium | High | PM | Implement 5 key producer hooks only in week 1 | Integration list keeps growing | Open

## Acceptance Checklist
Area | Acceptance Item | Owner | Required | Status | Evidence / Notes
Database | governance_events table created as append-only event store | Aayush | Yes | Not Started
Database | event_outbox, event_processing_log and event_dead_letter tables created | Aayush | Yes | Not Started
Database | event_schema_registry, retention rules and export log available | Aayush | Yes | Not Started
Database | Indexes support event type, occurred_at, correlation_id, subject and actor queries | Aayush | Yes | Not Started
Backend | Event publisher creates canonical event envelope and persists event | Pankaj | Yes | Not Started
Backend | Schema validation blocks incomplete or invalid events | Pankaj | Yes | Not Started
Backend | Outbox dispatcher retries and dead-letters failed events | Pankaj | Yes | Not Started
Backend | Timeline API reconstructs subject and correlation event chains | Pankaj | Yes | Not Started
Backend | Existing modules emit at least five key governance events | Aayush | Yes | Not Started
Security | Events cannot be updated/deleted through normal application path | Pankaj | Yes | Not Started
Security | Event access respects tenant, RBAC/ABAC and classification | Pankaj | Yes | Not Started
Frontend | Event Explorer supports search, filter and event detail | Poorvith | Yes | Not Started
Frontend | Audit Timeline displays ordered event lifecycle with actor and subject | Poorvith | Yes | Not Started
Frontend | Dead Letter Queue and retry action visible to admin role | Poorvith | Yes | Not Started
Frontend | Audit Export request panel logs export request | Poorvith | Yes | Not Started
QA | DB/API/UI/security/integration tests executed with evidence | Pankaj | Yes | Not Started
Delivery | Handover pack contains scripts, API docs, UI route list, QA evidence and open issues | PM | Yes | Not Started

## QA Scenarios
Test ID | Scenario | Type | Owner | Day | Expected Result | Status | Evidence
QA4-001 | Publish valid governance event | API/DB | Pankaj | 20-Jul-2026 | Event stored and outbox record created | Not Started
QA4-002 | Reject event missing actor or subject | Negative | Pankaj | 20-Jul-2026 | API returns validation error; no event persisted | Not Started
QA4-003 | Search events by event_type and date range | API | Pankaj | 20-Jul-2026 | Filtered results correct | Not Started
QA4-004 | Fetch full timeline by correlation_id | API/UI | Pankaj | 20-Jul-2026 | Ordered lifecycle returned and shown in UI | Not Started
QA4-005 | Verify event immutability | Security | Pankaj | 21-Jul-2026 | Update/delete blocked through app path | Not Started
QA4-006 | Outbox retry and dead-letter after failure | Integration | Pankaj | 20-Jul-2026 | Retries tracked and DLQ record created | Not Started
QA4-007 | Event Explorer loading/empty/error states | UI | Poorvith | 20-Jul-2026 | Correct UX states displayed | Not Started
QA4-008 | Event Detail Drawer payload rendering | UI | Poorvith | 20-Jul-2026 | Envelope and payload visible safely | Not Started
QA4-009 | Classification-based event visibility | Security | Pankaj | 21-Jul-2026 | Unauthorized user cannot view restricted events | Not Started
QA4-010 | Audit export request is logged | API/UI | Pankaj | 20-Jul-2026 | event_export_log record created | Not Started
QA4-011 | Producer hook emits model/agent/relationship/workflow event | Integration | Aayush | 20-Jul-2026 | At least 5 flow events created | Not Started
QA4-012 | Dashboard metrics show event counts and DLQ count | UI/API | Poorvith | 20-Jul-2026 | Widget values match API | Not Started

## Lists
Status | Priority | Owner | Workstream | RACI | Severity
Not Started | Critical | Project Manager | Database | R | Critical
In Progress | High | Aayush | Backend | A | High
Blocked | Medium | Pankaj | Frontend | C | Medium
At Risk | Low | Poorvith | Integration | I | Low
Completed |  | All | QA
Deferred |  | TBD | Documentation
On Hold |  |  | Project Management
DevOps
Security